# Justification for Emergency PRA Clearance for

# Medicare CAHPS Survey

Subject: The Centers for Beneficiary Choices (CBC) is requesting that the Paperwork Reduction Act (PRA) package for the Medicare CAHPS Survey be processed under 5 CFR 1320.13 (a)(2)(i) for emergency clearance.

Background:  This revised request for approval takes the OMB approved MA (OMB control number is 0938 0732) and FFS CAHPS (OMB control number is 0938-0796) instruments and adds new Prescription Drug Plan (PDP) questions as mandated in Medicare Prescription Drug, Improvement, and Modernization Act of 2003 (MMA).  This revised package request will continue to use the OMB control number is 0938-0732, but will merge the MA and FFS surveys into one package.  Specifically the MMA under Sec. 1860D-4 (Information to Facilitate Enrollment) requires CMS to conduct consumer satisfaction surveys regarding the prescription drug plan or the MA prescription drug plan pursuant to section 1860D-4(d) and report the results to Part D eligible individuals at least 30 days prior to the enrollment period.  There is an exception for unavailability of information for the first plan year it is offered and for the next plan year if it is impracticable or the information is otherwise unavailable.  This request for approval is to ensure that CMS is able to conduct the Medicare CAHPS surveys in time to publicly report the data for the open enrollment period in Fall 2007.

Development of the Medicare CAHPS surveys is a coordinated effort between CMS and the Agency for Healthcare Research and Quality (AHRQ) under a very tight timeframe.  Because persons with Medicare could not join a Prescription Drug Plan (PDP) until January 2006, testing of the PDP questions added to the survey could not begin until enrollees had enough experience with their plan.  Currently, AHRQ is field testing the PDP set of questions in the Medicare CAHPS (OMB No. 0935-0124) to be completed November 2006.  The new Medicare CAHPS survey reduced burden to respondents through use of a shortened version of the Medicare Advantage (MA) and Medicare fee-for-service (MFFS) set of questions.   With addition of questions on the experiences of persons enrolled in a Medicare prescription drug plan, the survey will permit aggregation of the data and presentation of CAHPS measures at levels representing MA and MA-PD plans, as well as stand-alone PDPs, and the original Medicare FFS health plan. Information from the data collected in these surveys will be publicly reported on Medicare.gov to assist beneficiaries in selecting among the health plan and prescription drug plan choices available during open enrollment in 2007.  Delay in implementing the Medicare CAHPS survey would cause CMS to not meet its legislative requirements to collect and report satisfaction information on MA plans, FFS, MA-PDs and PDPs and cause public harm by not providing information to the public to assist persons with Medicare in their plan choices available under the MMA.

The Centers for Medicare & Medicaid Services (CMS) has collected information on consumer health services experiences of people with Medicare coverage enrolled in Medicare Advantage health plans through annual implementation of the Consumer Assessment of Healthcare Providers and Systems (CAHPS) Survey (MA-CAHPS) since 1998.  In 2000, CMS began collecting similar information from people with Medicare enrolled in fee-for-service.  Results of these surveys have been presented in the Medicare & You handbook and have been made available to people with Medicare on the Medicare.gov web site.   Beginning in 2006, CMS is required to expand data collection in its CAHPS surveys to also include consumer satisfaction and experience of persons with Medicare in a MA-PD or PDP plan, if they have enrolled in one.

CMS will publish results from the MA-MFFS PDP CAHPS surveys on www.medicare.gov to assist beneficiaries in choosing a health plan. In the past, the measures published included two rating items (the overall rating of the health plan and the overall rating of health care), three composite measures of beneficiary experiences with health plans (getting needed care, getting needed care without long waits, and doctors who communicate well), and three single items (seeing a specialist, flu shots, and pneumonia vaccinations). The Medicare Options Compare on www.medicare.gov presents comparisons of these results for individual Medicare Advantage (MA) health plans available in a geographic area as compared with the state and national averages for MA plans and for fee-for-service (“original”) Medicare. Additionally, one composite measure is reported at the plan and state level, in the Medicare & You handbook.

The deadline for having Medicare CAHPS data available for the handbook is June 2007 and July 2007 for the web in order to have information for open enrollment in Fall 2007.  If the printing of the survey begins in December, as requested, this permits CAHPS survey results to be available by June. The schedule of timelines is as follows:

| Survey Activities | Deadline Dates |
| --- | --- |
| Begin printing of 600,000 surveys with personalized names of health and drug plans plans in English and Spanish Staff training materials for survey operations Mailout of prenotification letter First mailout of questionnaire Second mailout of questionnaire Telephone follow up begins Completion of data collection activities Begin data cleaning including data reconciliation between mail and telephone responses Creation of weights: person-level, plan-level and population based. Creation of Case Mix Adjustment variables Data analysis including developing plan level estimates, scoring of composites and public reporting estimates. | December 20, 2006 January 15, 2007 February 1, 2007 February 7, 2007 March 5, 2007 March 17, 2007 April 15, 2007 May 11, 2007 May 28, 2007 June 4, 2007 June 7, 2007 |
| Handbook/Web Data Measures Delivered | Final Deadline Date: June 15, 2007 |

We therefore request emergency OMB approval of the Medicare CAHPS questionnaire to meet the tight schedule for collection and reporting of Medicare health and prescription drug plan information in fulfillment of the MMA requirements.

| KEY PRECEDING EVENTS |
| --- |
| Date | Milestone |
| October 20, 2006 | Emergency Justification request submitted |
| October 24, 2006 | Emergency PRA package submitted |
| October 27, 2006 | OMB approval for Emergency Justification request |
| November 16, 2006 | Received finalized survey instrument from AHRQ and CAHPS grantees |
| November 17,2006 | PRA Federal Register Notice comment period begins |
| Dec 1, 2006 | Finalized instrument sent to OMB |
| December 4, 2006 | PRA Federal Register Notice 20 day comment period ends |
| Dec 18, 2006 | OMB approval |
| Dec 20, 2006 | Finalized survey is sent to printer in preparation for February fielding of the survey. |
| February 1, 2007 | Fielding of 2007 Medicare CAHPS survey is started |

Contact: 	Amy Heller amy.heller@cms.hhs.gov  410-786-9234 or Ted Sekscenski Edward.sekscenski@cms.hhs.gov 410-786-7167.