Attachment A1:  Proposed Time Schedule

| Task | Timeframe |
| --- | --- |
| Survey Data Collection | June 2007 - August 2007* |
| Semi-Structured Interview Collection | August 2007 – September 2007* |
| Data Analysis | July 2008 – September 2008* |
| Report Writing | August 2008 – September 2008* |

*Note:  Data collection will begin upon OMB approval.