National Survey on Drug Use and Health:

2007 Mental Health Module Feasibility Study

SUPPORTING STATEMENT

A.	JUSTIFICATION

- Purpose and Use of Information

The National Survey on Drug Use and Health (NSDUH), sponsored by the Substance Abuse and Mental Health Services Administration (SAMHSA), is a national survey of the U.S. civilian non-institutionalized population aged 12 and older.  The conduct of the NSDUH is paramount in meeting a critical objective of SAMHSA’s mission, i.e., to maintain current data on the prevalence of substance use in the United States.

This package is submitted under the NSDUH Methodological Field Tests generic OMB clearance (OMB No. 0930-0261).

In December, 2006 a meeting of expert consultants was convened by the Center for Mental Health Services (CMHS), SAMHSA to solicit recommendations for mental health surveillance data collection strategies.  The panel recommended conducting methodological studies to calibrate NSDUH mental health and impairment screening tools with a ‘gold standard’ clinical psychiatric interview to create a statistically sound measure that may be used to estimate the prevalence of Serious Mental Illness (SMI) among adults (age 18+).  A summary of this meeting is included in Attachment L.  Approved funding for FY 2007 and proposed funding for FY 2008 to carry out these recommendations is documented at http://www.samhsa.gov/Budget/FY2008/SAMHSA08CongrJust.pdf (see page PM-2 or page 126 of 188).  As an initial step, a small Feasibility Study in 2007 to test procedures for collecting data on an expanded mental health screener module and for conducting follow-up telephone psychiatric interviews with selected respondents is being proposed.  Information from this Feasibility Study will inform the design and protocol development for a full calibration study to be conducted as an embedded split-sample study within the 2008 NSDUH.

Creating a robust, sustainable mental health surveillance system using the NSDUH as the household survey vehicle will require three essential elements: 1) appropriate screening and gold standard measures; 2) seamless procedures to transfer respondents from the NSDUH to the clinical interview section of calibration study and 3) appropriate analysis of the data.  This Feasibility Study is aimed at identifying and pilot testing the administration of the measures and refining procedures to recruit respondents, to connect them with clinical interviewers for a follow-up interview, and to transfer interview information to the contractor (RTI) for data entry and analysis.

There are two types of mental health measures that will be used in this Feasibility Study – screening measures embedded in the NSDUH computer-assisted interviewing (CAI) survey and standard clinical interview measures that will be administered by mental health clinicians over the telephone.  The CAI screening measures will include the K-6 nonspecific distress scale (Kessler et al, 2003)  a brief suicidal ideation screen ( Borges,  et al, 2006), and two types of disability scales (the World Health Organization-Disability Assessment Scale (WHO-DAS) (Rehm et al, 1999) and the Sheehan Disability Scale (SDS) (Leon et al, 1997)).  The mental health module questions are listed in Attachment M.  The 2007 NSDUH CAI will be modified to include the additional scales to be administered to respondents participating in this Feasibility Study.  To mimic the anticipated split sample design of the 2008 study, respondents will be randomly assigned to receive only one of the two disability scales in the CAI.

The clinical interview measure to be used is the Structured Clinical Interview for DSM-IV- TR Axis I Disorders Non-patient Edition (SCID-I/NP, 1/2007 revision) (First, M; Spitzer, R; Gibbon, M; & Williams, J; 2007).  Recommended by our expert consultants, the SCID I/NP has been used for clinical calibration in several other studies such as the National Comorbidity Survey-Replication (NCS-R) (Kessler et al, 2004); the National Survey of American Life (Jackson et al, 2004), and the NSDUH  substance use disorders clinical reappraisal study (Jordan et al, 2003).  Dr. Michael B. First, author of the SCID interview will be our primary expert consultant on all matters associated with the adaptation and use of the SCID in the Feasibility Study.  Adaptations of the SCID will include modifying (shortening) the interview to assess mental disorders in the past 12 months (removing items used to assess lifetime disorder) and insuring each module is in the appropriate format for telephone administration.

Ten 10 non-active area segments previously used in the 2006 NSDUH survey will be used to test the procedural elements of the study.  The segments will be purposively selected based on having a sufficient number of remaining sample dwelling units and proximity to field interviewers selected to participate in the study.  Within these 10 segments, a sample of approximately 270 dwelling units will be selected with the expectation that NSDUH interviews with 56 persons aged 18 or older will be completed.  Field interviewers will administer the modified NSDUH questionnaire via computer assisted interviewing (CAI) using standard protocols (see section 2 - Use of Information Technology).  At the end of the CAI interview, Field Interviewers will attempt to recruit the respondents into the follow up study using the on-screen scripts created for this purpose (Attachment H).  Those that agree to participate will be given $30 that day and phone contact information will be collected so that the clinical interviewer may reach them in the following one to two weeks to do the SCID interview.  Respondents will be asked to identify best days and times for the interviewer to call.  Respondent first name, phone number and “best time to call” information will be transmitted to the clinical interviewer who will then schedule and conduct the interview.  For reference, the clinical interviewer will also record the date and time of the initial interview, along with the Record of Call history for the case.  Recognizing the tremendous importance of confidentiality with regard to the NSDUH, advance information (other than contact data) will not be provided to clinical interviewers.  Clinical interviewers experienced in administering the SCID will be recruited to participate in the Feasibility Study.  These clinical interviewers will be certified by SCID experts and will be provided supervision throughout the Feasibility Study to maintain the integrity and reliability of clinical assessment and to resolve any clinical issues or questions that emerge throughout the study period.

In the Feasibility Study, all persons who complete a NSDUH interview will be selected for follow-up.  It is expected that 48 of the 56 NSDUH interview respondents will participate in the follow-up clinical interview within the requisite (4 week) timeframe (see Exhibit 1: Mental Health Follow-up Feasibility Study Design Parameters).  Clinical Interviewers will telephone respondents to conduct the clinical interview based on the availability information provided in the initial interview.  Clinical interviewers will record identification numbers and responses on a paper and pencil version of the SCID and, with the respondent’s permission, will audiotape the interview.  Clinical interviewers will forward the paper SCID, along with the audio recording, to Columbia University for a QC review by experts in the SCID administration.  After this QC step, the paper SCID and audio recording will be sent to RTI for data entry.  This process will be conducted in a timely manner (at least weekly). The initial and follow-up interview data collection period for this study is June 1-June 30, 2007.  All data must be submitted to RTI for entry and analysis by July 6, 2007.

- Use of Information Technology

This Feasibility Study will use the 2007 NSDUH computer hardware and instrument, which will be adapted to include the full mental health module.  IPAQ hand-held computers will be used to conduct household screening interviews and Gateway laptops will be used to administer the NSDUH questionnaire via computer-assisted interviewing (CAI).  The NSDUH study has been administered via CAI since 1999.

The iPAQ will select initial interview respondents using a pre-programmed selection algorithm based on age gathered during the screening process.  Half of the selected participants will be aged 18-25 and the other half will be aged 26 and over.  As in the main NSDUH survey, field interviewers will roster all persons living in sampled dwelling units and the selection algorithm will automatically select 0, 1, or 2 persons.  Unlike the NSDUH, persons aged 12-17 will be assigned a selection probability of zero and will not be eligible to be selected for the initial interview.

Within the 2007 NSDUH Feasibility Study CAI, follow-up interview recruitment scripts will be administered at the end of the initial interview using computer-assisted personal interviewing (CAPI).  Respondents that decline to participate will be asked to provide the reason(s) why they do not wish to participate.  Contact information for those who agree to participate will be entered in the laptop.  This information will be posted to a secure website for access by the clinician assigned to contact the respondent for the follow-up interview. The follow-up SCID interview will be administered via telephone on a paper and pencil (PAPI) SCID instrument.

# 3.	Efforts to Identify Duplication

The Office of Applied Studies, SAMHSA, is in contact with all major federal health survey managers and is aware of no other efforts to calibrate mental health screening and impairment scales to a structured clinical interview to derive national estimates of Serious Mental Illness.  Mental health assessment experts convened in December 2006 and recommended a study such as this one to address a prominent data gap (See Attachment L), thus, there is no evidence of duplication of effort.

4.	Consequences if Information Collected Less Frequently

The focus of the Mental Health Module Feasibility Study is to test the procedures that may ultimately be proposed for a split-sample calibration study within the 2008 NSDUH.  This Feasibility Study must be conducted and analyzed by mid-summer, 2007 to provide enough time to incorporate findings into the 2008 NSDUH questionnaire.  This abbreviated schedule requires that the 4 week data collection portion of the study must be completed by June 30, 2007.

# 5.	Consultation

The following persons were consulted during 2006 and 2007 concerning plans for the NSDUH split-sample study.  These persons provided input on the specific diagnostic tool for follow-up clinical interview, and commented on the overall study design.

| Ron Kessler, PhD. (617) 423-3587 Professor Department of Health Care Policy Harvard Medical School Boston, MA | Michael First, M.D. (212) 543-5531 Professor of Clinical Psychiatry Department of Psychiatry Columbia University Medical Center New York, NY |
| --- | --- |
| Phillip Wang, MD, PhD (301) 443- 6233 Director, Division of Services and Intervention Research National Institute of Mental Health Bethesda, MD | Michael Schoenbaum, PhD (301) 435-8760 Senior Advisor for Mental Health Services, Epidemiology and Economics National Institute of Mental Health Bethesda, MD |
| Jeffrey Johnson, PhD (212) 543-5523 Associate Professor of Clinical Psychology Department of Psychiatry College of Physicians and Surgeons Columbia University New York, NY | Jeffrey Buck, PhD (240) 276-1959 Chief, Survey, Analysis and Financing Branch Center for Mental Health Services Substance Abuse and Mental Health Services Administration Rockville, MD |

There are no unresolved issues resulting from these consultations.

# Payment to Respondents

On October 18, 2001, the use of a $30.00 incentive was approved by OMB for use in the 2002 NSDUH survey.  OMB approved the continued use of the $30.00 incentive for the 2003 through 2007 NSDUHs.  The follow-up interview to be completed for the Feasibility Study will constitute an additional burden on respondents, and may make it more difficult to obtain respondent participation.  The one month data collection window to complete both the initial and the follow-up interview may further increase the likelihood that respondents will not participate. To maintain adequate response rates, SAMHSA believes it is necessary to offer respondents an additional $30 payment for completing the follow-up clinical interview.  Furthermore, to maintain adequate response rates, SAMHSA believes it is necessary to provide the $30 incentive at the end of the initial (NSDUH) interview, once the participant agrees to the follow-up interview.  Research studies have shown that providing incentives up front increase the likelihood that participants will complete an interview (Groves & Couper, 1998).   The cash payment for the follow-up interview is mentioned in the following respondent materials:  Follow-up Interview Recruitment Scripts [Attachment H], Follow-up Study Description [Attachment F], and Follow-up interview Payment Receipt [Attachment G].

# 7.	Methods to Maintain Confidentiality

Concern for the confidentiality and protection of respondents’ rights has always played a central part in the implementation of the NSDUH and will continue to be given emphasis.

The Feasibility Study will incorporate several procedures to ensure that respondents’ rights will be protected, including procedures developed for the main NSDUH.  The interviewer will introduce the follow-up interview with recruitment scripts [Attachment H]. These scripts will appear on the computer screen at the end of the initial CAI interview and will be read out loud to each interview respondent selected for the Feasibility Study.  As part of the process for obtaining informed consent for the follow-up interview, respondents will be given a Follow-up Study Description [Attachment F], which includes information on the Confidential Information Protection and Statistical Efficiency Act of 2002 (included as Title V in the E-Government Act of 2002, P.L. 107-347) and the protection that it affords.  Specifically, the Follow-up Study Description states that respondents’ answers will only be used for research and analysis and cannot be used for any other purpose.

For the initial NSDUH interview, interviewers will be thoroughly educated in methods for maximizing a respondent’s understanding of the government’s commitment to confidentiality.  Furthermore, interviewers will make every attempt to secure an interview setting in the respondent’s home that is as private as possible.  As in the main NSDUH survey, a confidentiality pledge [Attachment I] will be read and signed by all field interviewers during the project training process.

With the CAI methodology, all sensitive data are entered privately by the respondent, and completed interview data are electronically transmitted to the Contractor’s offices on a nightly basis via secured data transmission.  Interviewers are unable to review or to edit questionnaire data as the completed interview files are locked.  Also, once the respondent has completed the audio computer-assisted self-interviewing (ACASI) portion of the interview, the ACASI section is locked, so that the interviewer is unable to back up into this area and review the respondent’s most sensitive data.  The dwelling unit address information, which is maintained in a separate file for contractor use in sampling, fielding, and weighting cases, as well as the respondent’s phone number, will be destroyed when all final data files are delivered to SAMHSA and approval received by the SAMHSA Project Officer.

Although the respondent’s first name and phone number will be collected within the main interview, it will be used only for re-contact purposes.  Once the CAI data is transmitted and arrives at RTI, the respondent's name, phone number, and text regarding the best time to call will be split off into a separate database with only the random number ID for linkage.  The rest of the CAI data will be converted into SAS and merged onto the master file.

The follow-up interview will be conducted over the telephone by clinicians trained in the administration of the SCID.  All clinical interviewers will receive training on the importance of keeping all information learned from respondents confidential.  A confidentiality pledge will be read and signed by all clinical interviewers during the project training process [See Attachment I].

Follow-up interview materials are marked for identification by the interviewer using a randomly-generated 7-digit number.  The respondent’s address or other easily traceable marks will not be included on the SCID paper form.

The permanent sampling records will show only the general location in which interviews were conducted; there is no record of specific dwelling units contacted and no record of which addresses were selected for the Feasibility Study.

There will be no Privacy Act System of Records established for this effort.

# 8.	Questions of a Sensitive Nature

Many safeguards, including the mode of questionnaire administration, have been incorporated into the NSDUH study design in order to improve the collection of data on sensitive issues/information.   To ensure that the respondent feels comfortable enough to share their answer in the initial interview, he/she will enter his/her answers directly into the computer via ACASI administration.  The interviewer will not see the answers.

The follow-up interview will be delivered by mental health clinicians trained in administering the SCID and deriving DSM-IV diagnoses from structured clinical interviews.  The clinician will administer the SCID over the telephone from a private location in his/her home or office.  When calling to conduct the SCID, the clinician will ask the respondent to go to a private location for the duration of the interview.  The clinician will explain to the respondent that he/she knows only the respondent’s first name and telephone number and that this identifying information will be discarded by the clinician after the interview has been completed.  The clinician will repeat the confidentiality assurances and will ask for permission to audiotape the interview [Attachment J].  The clinician will note the respondent’s answers on a paper SCID response sheet and will keep the questionnaire in a secure location until mailing it to the Clinical Supervisor (Jeffrey Johnson, PhD) for review and quality control.  Dr. Johnson will in turn, mail the completed SCIDs to RTI for processing.  The only identifying information on the SCID questionnaire will be a randomly-generated 7-digit number to link the SCID data to the NSDUH data, which can only be linked by researchers at RTI who have signed confidentiality pledges [Attachment I] and who will use the data only for research purposes.  The paper SCID, along with the audiotape of the interview will be sent via Federal Express to Columbia University for a QC review by experts in the SCID administration.  After this QC step, the paper SCID and audio recording will be sent to RTI via Federal Express for data entry.  All paper SCIDs and audio recordings will be destroyed at the end of the Feasibility Study.

# 9.	Estimates of Annualized Hour Burden

The total sample size for the completed NSDUH Feasibility Study will be 48 completed follow-up interviews.  It is expected that 202 screenings will be completed.  Zero, one, or two persons will be selected from the screened households, resulting in 81 persons selected.  Based on the NSDUH experience, 70% of the selected persons are expected to complete the interview, resulting in 56 initial NSDUH CAI interviews.  Assuming 85% of the initial respondents will complete the follow-up interview, 48 completed follow-up interviews are estimated.

The experience with the 2007 NSDUH interview indicates that the average interview time is approximately 60 minutes.  Therefore, it is estimated that the average amount of time required to administer the 56 initial interviews will also be approximately 60 minutes.  The follow-up clinical interview is estimated to take on average, an additional 60 minutes. Administration of the screening questions will take an average of 5 minutes per dwelling unit and will only be completed prior to the initial interview.

The hourly wage of $13.99 was calculated based on weighted data from the 2005 NSDUH respondents' personal annual income.

The data collection field period for the Feasibility Study spans June 1-30, 2007.

The respondent burden for the Feasibility Study is shown in the following table.  The respondent burden for the Feasibility Study will be subtracted from the total hours and annualized costs cleared in the generic NSDUH Field Test OMB clearance package.  OMB clearance for the embedded split-sample study will be requested within the OMB clearance package submitted for the 2008 NSDUH Study.

Estimated Burden for 2007 NSDUH Feasibility Study

| Instrument | No. of Respondents | Responses per respondent | Hours per response | Total burden hours | Hourly Wage rate | Annualized hourly costs |
| --- | --- | --- | --- | --- | --- | --- |
| Screening | 202 | 1 | 0.083 | 17 | $13.99 | $238 |
| Initial Interview | 56 | 1 | 1 | 56 | $13.99 | $783 |
| Follow-up interview | 48 | 1 | 1 | 48 | $13.99 | $672 |
| Total | 202 | _ | _ | 121 | _ | $1,693 |

# 10.	Estimates of Annualized Cost to the Government

Total costs associated with the Feasibility Study are estimated to be $450,000 over a 6-month performance period.  Of the total costs, $300,000 is for contract costs, e.g., sampling, data collection, processing, reports, etc., and approximately $150,000 represents SAMHSA costs to manage/administrate the survey. The annualized cost is approximately $900,000.

# 11.	Time Schedule, Publication and Analysis Plans

The Feasibility Study results will be used to refine the 2008 NSDUH embedded split-sample study field procedures, materials, and instrumentation.  The sample size and design do not allow for statistical inference to be conducted beyond the specific geographic areas selected for the Feasibility Study.  Therefore, the analyses will be observational and anecdotal.  The follow-up interview response rates will be analyzed along with the reasons for follow-up refusal elicited during the recruitment phase.  Debriefings with the field and clinical interviewers will be conducted to learn from their experiences about recruiting for and conducting the follow-up interview.

The time schedule for the Feasibility Study is included below.

2007 NSDUH FEASIBILITY STUDY SCHEDULE

ACTIVITY	TIME FRAME

Design and select sample	March 2007

Generate required materials/assignments	March - April 2007

Finalize programming of NSDUH interview	April - May 2007

Prepare for and conduct field staff /clinical interviewer training	April - May 2007

Conduct Feasibility Study NSDUH and follow-up interviews 	June 2007

Data Analysis/Prepare summary of findings and

submit to OMB	July - August 2007

Produce final data file	August 2007

# 12.	Respondent Universe and Sampling Methods

The 2007 Feasibility Study is intended to test the Mental Health Module Follow-up Study field procedures, materials and instrumentation, as well as respondents’ reactions to the follow-up clinical interview.  After the completion of the Feasibility Study, the contractor will assess the findings and make any necessary refinements in preparation for the 2008 NSDUH split sample study.  The sample for the Feasibility Study will be non-probability based and will be chosen in states where experienced NSDUH field interviewers are available to do the fieldwork during June 2007. A sample of non-active 2006 NSDUH segments will be selected based on sufficiency of sample dwelling units remaining and proximity to field interviewers identified to work on the Feasibility Study.

Persons eligible for the Feasibility Study will be the civilian, non-institutionalized population aged 18 years old and older.  As in the main NSDUH survey, the target population for the Feasibility Study includes residents of non-institutional group quarters (e.g., shelters, rooming houses, dormitories) and civilians residing on military bases. Unlike the main NSDUH survey, persons aged 12 to 17 years old will not be eligible for selection in the Feasibility Study.

Exhibit 1 shows that approximately 270 selected dwelling units will be needed to yield a total of 48 completed clinical follow-up interviews.  This is assuming a 90% screening response rate (SRR) among eligible dwelling units, a 70% interview response rate (IRR) for initial interviews, and an 85% IRR for clinical follow-up interviews.  The expected overall response rate (ORR) is 54%.  Sample dwelling units will be selected from 10 retired 2006 NSDUH segments.  Within these dwelling units, 0, 1, or 2 persons will be selected for the initial NSDUH interview.

Exhibit 1.  Mental Health Module Feasibility Study Design Parameters

| Design Parameters |  | Counts |
| --- | --- | --- |
| Selected segments |  | 10 |
| Lines per segment |  | 27 |
| Selected lines |  | 270 |
| DU eligibility Rate |  | 0.83 |
| Eligible dwelling units |  | 224 |
| Expected screening response rate |  | 0.9 |
| Completed screenings |  | 202 |
| Expected yield 12 or older |  | 0.6 |
| Sample 12 or older |  | 121 |
| Sample 18 or older |  | 81 |
| Assumed response rate |  | 0.70 |
| Interview respondents 18 or older |  | 56 |
| Total selected for telephone SCID follow-up |  | 56 |
| Telephone response rate |  | 0.85 |
| Completed clinical interviews |  | 48 |

# 13.	Information Collection Procedures

The Feasibility Study screenings and initial interviews will be completed using the same procedures, and materials used on the 2007 NSDUH main study with the exception of the Lead Letter [Attachment A], Question and Answer brochure [Attachment B], Introduction and Informed Consent [Attachment E], Follow-up Study Description [Attachment F], Quality Control Form [Attachment V] and Follow-up interview Payment Receipt [Attachment G].  These materials have been slightly modified to reflect the Feasibility Study sample design.  Attachments N through U contain the materials currently used for the 2007 NSDUH survey that will be used in the Feasibility Study, but have not been modified for the Feasibility Study.  The initial CAI interview will primarily be the same, but will include the new Mental Health module.  Attachment C includes a copy of the NSDUH screening script, Attachment D provides a detailed document of all questions asked of respondents in the initial interview, and Attachment K includes a copy of the follow-up interview.

After completing an initial NSDUH interview, the field interviewer will read CAPI scripts describing the follow-up interview process to the respondent.  These recruitment scripts are provided in Attachment H.  The respondent will be unaware that they will be asked to complete another interview until these scripts are activated within the CAI program. If the respondent refuses to complete the follow-up interview at recruitment or at the time of follow-up clinical interview, the field or clinical interviewer will not recontact the household again.

The follow-up interview must be completed within a 4 week timeframe and/or by June 30, 2007, whichever comes first.  The interviewer will recruit the respondent for the follow-up interview immediately following completion of the initial interview and try to collect his/her phone number and best days of the week and times of the day within two weeks for a clinical interviewer to complete the follow-up interview.  This contact information will be entered into the password-protected laptop.  All respondents that agree to participate in the follow-up interview will receive a $30.00 cash payment and a field interviewer-signed Follow-up interview Payment Receipt from the interviewer [Attachment G].

The selected follow-up interview respondents will be given a copy of the Follow-Up Study Description [Attachment F] at the end of the initial interview as part of the follow-up interview recruitment process.   If they agree to participate in the follow-up interview, respondents will be given $30 and a Follow-Up Interview Payment Receipt [Attachment G] by the field interviewer.  The selected follow-up interview respondent will also be read an introductory informed consent script [Attachment J] by the clinician, prior to any follow-up interview data collection.

# 14.	Methods to Maximize Response Rates

The primary method used to maximize response rates in the Feasibility Study will be prepaid $30 cash for agreeing to complete the follow-up interview, given to the respondent during the recruitment phase.

With a $30.00 incentive for the initial interview and an additional, up-front $30.00 incentive for the follow-up interview, the Contractor expects to obtain a 70% interview response rate (IRR) for initial interviews and an 85% IRR for follow-up interviews.  An overall response rate (ORR) of 54% is expected for the Feasibility Study.

The field interviewers will not be recontacting households to convert follow-up interview refusals, but they will be trained to answer respondent questions at the time of recruitment as appropriate.

To maximize clinical interview response rates, the clinical interviewers will use the best day/best time information obtained by the field interviewer to schedule interviews, but they will also be flexible in scheduling a time for the follow-up interview.  If a respondent is unavailable when the clinician calls to complete the follow-up interview, the clinician will schedule a callback appointment that is most convenient for the respondent.  Clinicians will be trained to thoroughly explain the study, its purpose, and answer questions from respondents.

# 15.	Tests of Procedures

The activities to be conducted under this approval are in themselves tests of procedures.

# 16.	Statistical / SAMHSA Consultants

| Arthur Hughes (240)276-1261 Project Officer/Mathematical Statistician Division of Population Surveys SAMHSA | James Chromy, Ph.D. (919)541-7019 Chief Scientist and Director of Statistical Operations RTI International |
| --- | --- |
| Joseph Gfroerer (240)276-1262 Director/Mathematical Statistician Division of Population Surveys SAMHSA | Ralph Folsom, Ph.D. (919)541-6248 Chief Scientist and Director of Small Area Estimation RTI International |
| Peggy Barker Statistician Division of Population Surveys SAMHSA | Lisa Colpe, PhD, MPH Senior Program Management Officer Division of Population Surveys SAMHSA |
| Dan Foley, M.A. Statistician, Survey, Analysis and Financing Branch Center for Mental Health Services SAMHSA | Ingrid Goldstrom Social Science Analyst Survey, Analysis and Financing Branch Center for Mental Health Services SAMHSA |

References

Borges, G., Angst, J., Nock, M.K., Ruscio, A.M., Kessler, R.C. (2006). Risk factors for the incidence and persistence of suicide-related outcomes: A 10-year follow-up study using the National Comorbidity Surveys. Journal of Affective Disorders.

First, Michael B.; Spitzer, Robert L., Gibbon, Miriam, and Williams, Janet B.W. (2007): “Structured Clinical Interview for DSM-IV- TR Axis I Disorders Non-patient Edition (SCID-I/NP, 1/2007 revision)” http://www.scid4.org.

Groves, R.M. and Couper, M.P. (1998). Nonresponse in Household Interview Surveys, New York: Wiley. pp. 282-284.

Jackson, J., Neighbors, H., Nesse, R., Trierweiler, S. and Torres, M. (2004). Methodological Innovations in the National Survey of American Life. The International Journal of Methods in Psychiatric Research. 13(4):289-298.

Jordan, BK, Karg, RS, Batts, K and Wiesen, CA (December 2003). Statistical Report of the Concordance of the Substance Abuse and Dependence Module of the 2001 NSDUH and Structured Clinical Interview for Substance Use Disorders.  Report to the Office of Applied Studies (OAS) of the Substance Abuse and Mental health Services Administration (SAMHSA), 2003.

Kessler, R.C., Abelson, J., Demler, O., Escobar, J.I., Gibbon, M., Guyer, M.E., Howes, M.J., Jin, R., Vega, W.A., Walters, E.E., Wang, P., Zaslavsky, A., Zheng, H. (2004). Clinical calibration of DSM-IV diagnoses in the World Mental Health (WMH) version of the World Health Organization (WHO) Composite International Diagnostic Interview (CIDI).  International Journal of Methods in Psychiatric Research. 13(2):122-139.

Kessler, R., Barker, P., Colpe, L., Epstein, J., Gfroerer, J., Hiripi, E., Howes, M., Normand, S-L., Manderscheid, R., Walters, E., Zaslavsky, A. (2003). Screening for serious mental illness in the general population. Archives of General Psychiatry. 60(2): 184-189.

Leon, A, Olfson, M., Portera, l., Farber, l., Sheehan, D. (1997) Assessing psychiatric impairment in primary care with the Sheehan disability Scale.  International Journal of Psychiatric Medicine. 27 (2): 93-105.

Rehm, J., Ustun, B., Saxena, S., Nelson, C, Chatterji, S, Ivis, F., Adlaf, E. (1999). On the development and psychometric testing of the WHO screening instrument to assess disablement in the general population.  International Journal of Methods in Psychiatric Research. 8:110-123.

ATTACHMENTS

Attachment A - 	Lead Letter

Attachment B - 	Q&A Brochure

Attachment C -	HU Screening Script

Attachment D - 	CAI Questionnaire Content

Attachment E -	Introduction and Informed Consent Statement

Attachment F -	Follow-up Study Description

Attachment G -	Follow-up Interview Payment Receipt

Attachment  H -	Follow-up Interview Recruitment Scripts

Attachment  I -	NSDUH Confidentiality Pledge

Attachment  J -	Follow-up Interview Introduction Script

Attachment  K -	SCID Content

Attachment L - 	December 6, 2006 Mental Health Data Meeting Minutes

Attachment M - 	Mental Health Module Questions

Attachment N - 	Initial Interview Study Description

Attachment O - 	Initial Interview Payment Receipt

Attachment P - 	Showcards/Pillcards

Attachment Q - 	‘Sorry I Missed You’ Card

Attachment R - 	Appointment Card

Attachment S - 	Certificate of Participation

Attachment T - 	Highlights from the 2005 NSDUH

Attachment U - 	NSDUH Newspaper Articles

Attachment V - 	Initial Interview Quality Control Form