Timeline for the Multi-Ethnic Study of Atherosclerosis

Month        		1      7     1     7     1     7     1     7     1     7     1     7     1     7     1     7     1     7     1     7     1     7     1     7

Year       	          99   99    00   00   01  01    02   02   03   03   04   04   05   05   06   06   07   07    08   08   09   09   10   10

Contract                   |-----------------------------------------------First Project Period-------------------------------------||------Renewal------>

Develop

protocol    	          |-----------|

Baseline

Examination	    		         |----Exam 1-----|

Follow-up

Examinations		        				   |---Exam 2---| |--Exam 3---| |-----Exam 4-----|

Follow up CT		        				   |-----50%-----| |-----50%-----| |------25%--------|

Follow up US        	        				   |-----50%-----| |-----50%-----|

Follow up MRI       				 					 |----Tagging----|

Morbidity/

mortality follow up  			|-------------------------------------------------------------------------------------------------------------------->

Analysis/

publication        			|-------------------------------------------------------------------------------------------------------------------->

Ancillary Studies   			  EXPOSURE DRIVEN		 	OUTCOME DRIVEN

(e.g., cohort collection) 		           (e.g., nested Case-Control)