UPDATED TIMELINE\* FOR THE ELECTRONIC HEALTH RECORDS (EHR) DEMONSTRATION EVALUATION

March 2, 2010

Mar. 2008 --- Evaluation contract awarded

June 2008 --- Demonstration sites selected

June 2009 --- Demonstration start date

Mar .2010 --- Office systems survey (OSS) – treatment group

May 2010 --- Site visits (round 1)

Mar. 2011 --- OSS (treatment and control practices)

Mar. 2012 --- Withdrawn practices interviews

 OSS (treatment practices)

Mar. 2013 --- OSS (treatment practices)

Mar. 2014 --- Site visits (round 2)

 OSS (treatment and control practices)

May 2014 --- demonstration ends

Feb. 2016 --- Evaluation ends

---------------------------------------

Note: Medicare claims data will be collected annually for treatment and control group practices.

UPDATED TIMELINE FOR THE MCMP DEMONSTRATION EVALUATION

Jan. 2010 --- OSS (treatment and comparison group practices)

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

\*Replaces Figure I.1 (page 14) in the PRA Supporting Statement dated April 10, 2009

UPDATED EHRD DELIVERY SCHEDULE OF REPORTS\*

March 3, 2010

Report Due Date\_\_\_\_\_\_

Implementation analysis report September 2010

Interim evaluation report November 2012

Evaluation summary report November 2013

Final site visit report May 2015

Evaluati0n final report February 2016

Final cost monitoring report February 2016

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

\*Updates TABLE B.6 (page 31) of supporting statement.