7417.1 REV-1

________________________________________________________________________

CHAPTER 12.  PROJECT CONSTRUCTION AND COMPLETION

Section 1.  Introduction

12-1.  GENERAL.  This chapter establishes the procedures for PHA

administration of the construction contract and the contract

of sale, inspections during construction, acceptance of the

construction work, and settlement upon project completion.

If assistance is required, the PHA should contact the AE Chief

or the designated construction analyst who will provide guidance

and assistance to the PHA.  Except where otherwise specified,

the following terms are used throughout this chapter:

a.  Contract.  This term refers to the construction contract

(conventional) or the contract of sale (turnkey).

b.  Contractor.  This term refers to the general contractor

(conventional) or the developer (turnkey).

c.  Construction.  This term refers to new construction and

rehabilitation.

12-2.  CONSTRUCTION CONFERENCE.  A construction conference will be held

within ten (10) calendar days of execution of the contract by

the PHA and the contractor to discuss the public housing program

construction requirements.  This is necessary to provide for the

timely construction of the proposed project by eliminating any

misunderstanding of the program regulations and procedures,

contract requirements, and the responsibilities of the PHA,

the PHA architect, the contractor, and the Area Office.

a.  Participants.  The AE Chief will coordinate the meeting

and will lead the discussion.  The designated construction

analyst and representatives from the Labor Relations Staff

and the FHEO Division shall attend to discuss and answer

questions concerning their technical requirements.  The MHR

shall also attend the meeting.  The PHA Executive Director,

or designee, the PHA architect, and the contractor and any

subcontractors shall also attend the meeting.

b.  Discussion Items.  The PHA may submit a list of specific

discussion items (including items identified by the

contractor) to the construction analyst prior to the

date scheduled for the construction conference.  In

addition to the items identified by the PHA, the following

should be discussed:

________________________________________________________________________

12-1                               10/80

________________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(1)  the content and requirements of the contract;

(2)  the project construction and completion requirements

identified in this chapter;

(3)  the PHA and contractor insurance requirements

identified in Chapter 3 (Section 3);

(4)  the FHEO requirements identified in Chapter 3

(Section 4);

(5)  the prevailing wage rate requirements identified in

Chapter 3 (Section 2); and

(6)  the need for the PHA to promptly notify the construction

analyst of any problems being encountered so that

assistance may be provided by the Area Office staff

to keep project construction on schedule.

c.  Minutes of Meeting.  The construction analyst,

immediately following the construction conference, shall

prepare a summary of the items discussed at the meeting.

A copy of this summary shall be sent to each of the Area

Office participants and to the PHA.

12-3 thru 12-10.  RESERVED.

________________________________________________________________________

12-2 thru 12-6

10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

Section 2.  Contract Administration

12-11.  PUBLIC HOUSING AGENCY.  The PHA pursuant to the ACC is responsible

for enforcing the PHA architect's contract and the construction

contract or contract of sale and for ensuring retention of all

contractual rights.

a.  Contracting Officer.  The PHA shall designate an employee

as its contracting officer.  The scope and limitation of

the contracting officer's responsibility shall be identified

in writing and copies shall be provided to the PHA architect

and the contractor.

b.  Contract Administrator.  The PHA shall designate a qualified

professional to administer the contract.  Unless otherwise

authorized by the Area Office, the PHA architect will be

designated as the contract administrator.

c.  Start of Work.  The PHA shall advise the AE Chief in writing

of the date that construction work begins.  The PHA letter

shall also indicate for conventional projects that the

evidence of insurance (Chapter 3, Section 3) has been

received by the PHA and is in compliance with the construction

contract.

d.  Reports.  The PHA shall obtain the reports and construction

documents required by the contract and this chapter from the

PHA architect and contractor.  A copy of these reports will

be retained by the PHA and, as required, a copy will be sent

to the AE Chief.

e.  HUD Construction Forms.  The PHA shall maintain a supply of

required HUD Forms for use by the PHA, the PHA architect,

and the contractor.  An initial supply of HUD Forms will be

provided by the Area Office upon approval of the contract

(paragraph 12-13).

f.  Construction Progress Meetings.  The PHA Executive Director

shall meet with the PHA architect and the contractor on a

monthly basis.  These meetings will be held to discuss

the progress of construction work, any problems or

deficiencies noted during inspection visits, overdue reports

and the construction schedule.  The PHA shall prepare a

written record of the items discussed at each meeting and a

copy shall be placed in the PHA project construction file.

________________________________________________________________________

12-7                            10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

g.  Correction of Deficiencies.  The PHA, upon being notified by

the PHA architect or the Area Office construction analyst

of construction deficiencies, shall promptly notify the

contractor in writing of the deficiencies observed.  This

notification shall also advise the contractor that failure

to make timely corrections would be an infraction of the

contract and that the contractor is liable for any resulting

losses or delays.

12-12.  PHA ARCHITECT.  The PHA architect is responsible for ensuring

that the project is constructed in accordance with the construction

documents approved by the Area Office, as well as applicable State

and local requirements.

a.  Basic Services.  The PHA architect, as an agent of the PHA,

is responsible for providing the services identified in the

PHA architect's contract such as:

(1)  making periodic site visits to determine the quality

and progress of work and compliance with the contract;

(2)  advising the PHA of any deficiencies noted and preparing

a notification to the contractor to correct such work;

(3)  preparing applicable change orders (conventional) to the

contract and submitting change orders to the PHA for

Area Office approval;

(4)  for conventional projects, reviewing the contractor's

schedule for construction contract payments and

recommending payments to be made by the PHA in

accordance with the contract; and

(5)  participating in the final inspection, identifying

punch list items and amounts to be withheld until such

work is corrected, and signing the project completion

documents.

b.  Additional Services.  The PHA architect's contract may

require the architect to employ representatives to provide

daily on-site supervision of work in progress.  This

generally will be limited to projects with more than fifty

(50) units.  In such instances, the number of on-site

inspectors specified in the PHA architect's contract shall

not exceed the following:

________________________________________________________________________

10/80

12-8

_____________________________________________________________________

7917.3- REV-1

________________________________________________________________________

(1)  Projects of fifty (50) to one hundred (100) units:  one

full-time inspector for the entire contract period; or

(2)  Projects of more than one hundred (100) units:  one

full-time "clerk of the works" for the entire contract

period and one full-time inspector for one-half of the

contract period.

c.  Reports.  The PHA architect shall prepare and promptly submit

the following reports to the PHA:

(1)  Deficiencies:  a written report of any deficiencies or

disputes that the PHA architect brought to the

contractor's attention but which the contractor has not

corrected or has refused to correct; and

(2)  Construction Report:  a Construction Report (Form HUD

5378) shall be prepared on the first and sixteenth day of

each month during the construction period -- from the

date of contract execution to final inspection.

12-13.  AREA OFFICE.  The Area Office is responsible for ensuring that the

PHA, in accordance with the terms of the ACC, is enforcing the

PHA architect's contract and the construction contract or

contract of sale, including the construction documents approved

by the Area Office.

a.  General.  The Area Office will provide technical assistance

and guidance to the PHA concerning contract administration

and enforcement, reporting, interpretation of construction

documents, and other related matters such as:

(1)  PHA supervision of the PHA architect and contractor;

(2)  completing standard HUD Forms;

(3)  reviewing and approving change orders and revisions

to the construction documents;

(4)  PHA acceptance of completed work; and

(5)  procedures for resolving disputes and contract

enforcement by the PHA.

________________________________________________________________________

12-9                            10/80

_____________________________________________________________________

7417.1 REV-1 CHG-5

________________________________________________________________________

b.  HUD Construction Forms.  As soon as the contract is approved by

the Housing Development Division Director, the PCR Unit shall

send a sixty (60) day supply of standard HUD Forms to the PHA.

(1)  Turnkey Projects:  The following HUD Forms shall be sent:

Number                Title

*        Form HUD 5372         Construction Progress             *

Form HUD 5378         Construction Report

Form HUD 51002        Schedule of Change Orders

(2)  Conventional Projects:  The following HUD Forms as well as

the HUD Forms for turnkey projects shall be sent:

Number                Title

*        Form  HUD 51000       Schedule of Amounts for Contract   *

Payments

Form  HUD 51001       Periodic Estimate for Partial

Payment

Form  HUD 51003       Schedule of Materials Stored

(3)  Site Visits.  The construction analyst, designated by the

AE Chief all visit the construction site at least monthly

to evaluate project construction and PHA administration

activities.  The construction analyst shall review such

matters as the following:

(1) general performance of the PHA in administering all

project related contracts in accordance with the ACC;

(2) PHA records to determine that required insurance

coverage is in force;

________________________________________________________________________

8/88                                12-10

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(3)  construction work, material, and equipment to determine

that the contract requirements are being met; and

(4)  the contractor's payroll records, employment practices,

material invoices and project accounting records, to

ensure the contract requirements are being met.

d.  Reports.  The construction analyst, upon concluding each

site visit, shall discuss any observations or findings

with the PHA Executive Director or PHA architect and advise

the PHA to take necessary action to correct any deficiencies

that were observed.  The construction analyst shall

subsequently prepare a HUD Representatives Trip Report

(Form HUD 5379) and submit it to the AE Chief and send a

copy to the PHA.

12-14 thru 12-20.  RESERVED.

________________________________________________________________________

12-11 thru 12-16                 10/80

_____________________________________________________________________

7417.1 REV-1 CHG-5

________________________________________________________________________

Section 3.  General Requirements for Project Construction

12-21.  SUBCONTRACTORS.  All contracts between the contractor and any

subcontractors shall contain the FHEO employment requirements

(Chapter 3, Section 4) and the prevailing wage rate requirements

(Chapter 3, Section 2).  The contractor is responsible for

determining that potential subcontractors are not on the HUD

consolidated list of debarred, suspended or ineligible contractors.

12-22.  CONTRACTOR PAYROLL.  The contractor is responsible for paying

prevailing wage rates (Chapter 3, Section 2) to all employees

engaged in work under the contract and ensuring that any

subcontractors also pay prevailing wage rates.

a.  Payroll Report.  The contractor shall submit a certified

payroll report to the PHA each week during the contract period

--i.e., from execution of the contract to project completion

and acceptance by the PHA.  A separate payroll report shall be

submitted for the contractor and subcontractor.

b.  Payroll Forms.  The contractor's report shall be submitted on

the Payroll Form (WH 347) and Statement of Compliance (WH 348).

Such forms can be obtained from the Government Printing Office,

Washington, D.C. 20402.  The contractor may substitute

computer generated forms, instead of the Payroll Form (WH 347),

provided that all of the required information is included.

c.  Retention.  The PHA shall retain all payroll reports for three

years from the date of project completion and acceptance by the

PHA.

12-23.  AS-BUILT DRAWINGS.  The PHA shall be provided with a copy of the

as-built drawings for its project construction file upon project

completion.  These drawings shall include all significant

deviations from the working drawings approved by the Field Office.

a.  Responsibility.  The as-built drawings shall be prepared as

follows:

(1)  Turnkey projects:  The turnkey developer is responsible

for preparing and submitting the as-built drawings to the

PHA.

________________________________________________________________________

12-17 and 12-18                       8/88

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(2)  Conventional projects:  The general contractor is

responsible for providing all necessary information

to the PHA architect in order that the PHA architect

may prepare the as-built drawings.

b.  Utilities.  The proposed underground utility lines are

usually identified on the working drawings in diagram form.

The actual location of underground utilities shall be

recorded on the as-built drawings to indicate:

(1)  the depth of underground lines from finished grade

and the distance from buildings;

(2)  the depth from finished grade and the distance from

buildings of related underground work such as bands,

cleanouts, connections, branches, cutoffs and sewer

ends; and

(3)  the invert elevations of the storm and sanitary sewer

systems.

c.  Other.  All significant deviations from the working drawings

shall be noted on the applicable architectural sheet.

Detailed descriptions and changes may be made to the

applicable sheet or a note may be made referring to

attachments, other sheets, or to change orders.  Separate

attachments or drawings shall cross reference the related

architectural sheet.

12-24.  PHA SUBMISSION OF CHANGE ORDERS.  The PHA shall not order or

agree to any changes in the contract work without the prior

written approval of the Area Office.  Changes in construction

work that are beyond the scope of the contract shall be limited

to work that is required to provide a necessity, appropriate

betterment, or equivalent, for the proposed project.

a.  Limitation.  Changes in work shall be authorized by the

Area Office only when such changes are clearly in the

interest of the PHA.  Changes generally will be limited

to work required for the safety of the occupants or to

protect the structural soundness of the project.  In

addition, the cost of such changes must be within the

applicable project prototype cost limit.

b.  Preparation.  Change orders shall be prepared by the following:

(1)  Turnkey projects.  The turnkey developer is responsible

for preparing and submitting change orders to the PHA.

________________________________________________________________________

12-19                               10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(2)  conventional projects.  The PHA architect is responsible

for determining whether a change is necessary and

preparing and submitting change orders to the PHA.

The general contractor is responsible for submitting

any information required by the PHA architect.

c.  Content.  Changes in contract work shall be documented by a

change order.  A change order is a written agreement, executed

by all parties to the contract, which describes the changes

in work to be performed.  Change orders shall be prepared

in the form prescribed by the Area Office and shall include

the following:

(1)  a detailed description of the proposed change in work;

(2)  a reference to the applicable working drawings and

specifications;

(3)  a fixed price (credit, debit, or no change) for the

change in contract work;

(4)  an estimate of any additional time required to complete

the work;

(5)  the contractor's itemized breakdown of the cost of

materials and labor and, for conventional projects, an

itemized breakdown for any applicable subcontractors; and

(6)  the change indicated on the architectural drawings, if

applicable.

d.  Submission.  A proposed change order shall be signed by

the PHA architect and by the contractor and the PHA.  A

copy of each proposed change order and the supporting

documentation shall be submitted to the Area Office for

review and approval.

e.  Numbering.  The PHA shall assign a consecutive number to

each change order submitted to the Area Office.  The prefix

"T" shall be used for turnkey projects and "G" for conventional

projects.  However, for conventional projects having separate

trade contracts the following prefixes shall be used:

demolition (D); plumbing (P); heating (H); electrical (E);

and landscaping (L).

________________________________________________________________________

10/80                           12-20

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

f.  PHA Register.  The PHA shall maintain a separate change

order register for each project--i.e., on a project-by-project

basis.  This is required to provide a permanent

record of all actions taken in connection with each project.

The register shall identify:

(1)  the change order number;

(2)  a brief description of the change;

(3)  the cost of the proposed change;

(4)  the date submitted to the Area Office;

(5)  any critical deadline dates that must be met by the

Area Office;

(6)  the date of Area Office approval or disapproval, and the

action taken; and

(7)  the amount of any additional time required by the

contractor.

12-25.  AREA OFFICE APPROVAL OF CHANGE ORDERS.  The AE Chief is responsible

for coordinating the review and recommending approval (or

disapproval) of change orders by the Housing Director.

a.  Standard Processing Time.  The standard processing time (SPT)

is the number of calendar days from receipt of the proposed

change order by the PCR Unit and a decision by the Housing

Director.  The SPT for Area Office review and action on a

change order is ten (10) calendar days.

b.  AE Branch.  The AE Chief, in order to recommend approval,

shall determine, with respect to the proposed change that:

(1)  it is not within the scope of the contract;

(2)  it is a necessity and in the interest of the PHA;

(3)  it is consistent with the standards for the public

housing program;

(4)  it cannot practicably be performed under a separate

contract after completion of the project; and

(5)  any additional time required for the change is

reasonable.

________________________________________________________________________

12-21                           10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

c.  Cost Branch:  The Cost Chief in order to recommend approval

shall determine and advise the AE Chief that:

(1)  the fixed price for the change order is reasonable; and

(2)  any additional costs can be approved based on the

project prototype cost limit.

d.  Mortgage Credit Branch.  The Mortgage Credit Chief shall

review the proposed change order to determine that any

additional costs can be made available from the contingency

account.

e.  AHM Branch.  Change orders that would affect project management

or maintenance operations (e.g., substitute materials or

equipment, changed utility combinations) shall be submitted to

the AHM Branch for review.  The AHM Chief shall promptly submit

any recommendations to the AE Chief.

f.  Legal Division The Area Counsel shall be requested to provide

assistance if there is reason to believe that a proposed

change is within the scope of the original contract, or to

correct work which is the responsibility of the PHA architect

or the contractor.

g.  PHA Notification.  The AE Chief, upon determining that the

change order is approvable, shall sign the change order as

the authorized Area Office official if signature authority

has been delegated by the Housing Director.  If a change

order is disapproved, a letter shall be prepared for the AE

Chief's signature, if signature authority has been delegated,

advising the PHA of the reasons for disapproval.

12-26.  TIME EXTENSIONS.  The contractor is responsible for completing

the project within the time established in the contract.

Accordingly, the PHA shall not authorize any time extensions

without the prior written approval of the Area Office.

a.  PHA Records.  The PHA, upon project completion, shall

determine the number of calendar days and reasons for any

delays beyond the date established in the contract.  The

PHA shall maintain a record of potential causes for delays

which will be used as the basis for granting time extensions

or for determining the amount of liquidated damages to be

assessed against the general contractor for conventional

projects (paragraph 12-46).  The PHA shall maintain a record

of the following:

________________________________________________________________________

10/80                           12-22

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(1)  the daily temperature;

(2)  the daily amount of precipitation;

(3)  delays in obtaining labor and materials, including the

duration and reason;

(4)  labor disputes or strikes, including the duration,

and the applicable construction trade;

(5)  delays experienced by others in completing non-contract

public improvements (whether on-site or off-site); and

(6)  other causes for delays, such as fires, floods, vandalism

or court orders.

b.  Basis for Time Extensions.  In order to be considered for

approval by the Area Office, requests for time extensions

must meet the following criteria:

(1)  the contractor must have submitted a written notice to

the PHA within ten (10) calendar days of the start of

any delay;

(2)  the severity and extent of adverse weather could not

have been reasonably foreseen by the contractor (normal

seasonal levels of rain, snow, cold, or heat should

have been considered by the contractor);

(3)  the cause of the delay was beyond the contractor's

control; and

(4)  any additional cost attributable to the delay is

being borne by the contractor.

c.  Contractor Request.  The PHA immediately upon receipt of

a contractor's notification of delay or request for time

extension shall send a letter of acknowledgement to the

contractor.  The letter shall indicate:

(1)  immediate attention will be given to the contractor's

request and that a "finding of fact" will be submitted

to the Area Office for consideration and approval; or

(2)  the actual delay in the work is difficult to determine

and a "finding of fact" will be sent to the Area Office

for consideration and approval upon completion of work.

________________________________________________________________________

12-23                        10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

d.  PHA Finding of Fact.  The PHA shall review its records to

ensure that the information provided by the contractor is

accurate, to determine the cause of the delay and the

extent that it was within the general contractor's

control, and the request meets the criteria established

in subparagraph b.  The PHA, based on its review, shall

prepare a "finding of fact" with the assistance of the

PHA architect and PHA attorney and submit its recommendation

to the Area Office for approval.

e.  Area Office Approval.  The AE Chief shall review each PHA

"finding of fact".  In order to recommend approval, the AE

Chief must determine that:

(1)  the contractor's request, as documented by the PHA

"finding of fact," meets the requirements of

subparagraph b;

(2)  the additional time requested by the contractor is

reasonable based on the nature and duration of the

delay; and

(3)  if there is some question of the contractor's liability

for the delay, the PHA "finding of fact" shall be

reviewed in accordance with paragraph 12-27.

12-27.  DISPUTES AND CLAIMS.  The PHA shall promptly notify the Area

Office of any problems or disputes experienced during construction

which could result in a claim by the PHA architect or the

contractor.  This may include claims for extra costs due to

delays, claims for time extensions or extra costs based on PHA

actions, or claims resulting from contract changes.

a.  PHA Records.  It is imperative that the PHA maintain a

complete written and dated record of any actions that may

result in a dispute or claim for damages.  This is required

to protect the PHA interest during any litigation

proceedings that may subsequently arise.  In such instances,

the PHA shall, at a minimum, maintain the following:

(1)  a complete and detailed (daily job record;

(2)  a disputes and claims file, cross-referencing other

pertinent files, for each dispute or claim, and

(3)  any correspondence relating to the dispute, including

written minutes of any meetings, which identify

actions taken by the PHA, PHA architect or contractor

and decisions or agreements made concerning the dispute.

________________________________________________________________________

10/80                              12-24

_____________________________________________________________________

7417.1 REV=1

________________________________________________________________________

b.  Contractor Notice.  The contractor must submit a written

notice of claim to the PHA within ten (10) calendar days

from the date of the incident on which the claim is based.

The contractor's initial notice must identify the nature and

scope of the claim, including extra costs sought by the

contractor.  The contractor will subsequently be required to

submit a detailed description and supporting evidence for

the claim.

c.  PHA Acknowledgement.  The PHA immediately upon receipt of

a contractor's notice shall date stamp the notice and shall

send a letter to the contractor acknowledging receipt of the

claim.  The PHA's letter shall also indicate:

(1)  if the claim was filed within the ten (10) day period,

that the contractor is required to submit a detailed

justification for the claim; or

(2)  if the claim was not filed within the ten (10) day period,

the contractor's claim is not eligible for consideration.

d.  PHA Finding of Fact.  The PHA shall review its records to

assure that the information provided by the contractor is

accurate.  The PHA, based on its review of the contractor's

claim and its knowledge of the circumstances, shall prepare

a "finding of fact" with the assistance of the PHA architect

and PHA attorney and submit its recommendations for a

determination by the Area Office.

e.  Area Office Approval.  The AE Chief, in conjunction with the

Area Counsel, shall review the PHA "finding of fact" and

proposed disposition of the claim.  In making this review,

consideration shall be given to the contractor's claim

and the PHA recommendations in light of the obligations

of both parties under the contract.  Upon completion of

the review, the AE Chief shall prepare a letter for the

Housing Director's signature (with the concurrence of the

Area Counsel) instructing the PHA to promptly:

(1)  notify the contractor of the PHA decision (as approved

by the Area Office);

(2)  if applicable, request the PHA architect to prepare a

change order to reflect any modifications to the contract

as a result of the decision;

(3)  notify the Area Office, if the Area Office decision is

not acceptable to the PHA; or

________________________________________________________________________

12-25                           10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(4)  notify the Area Office, if the contractor does not

accept the decision (if court action is taken, the

PHA shall submit a copy of the contractor's assertions

to the Area Office).

12-28 thru 12-40.  RESERVED.

________________________________________________________________________

10/80                          12-26 thru 12-32

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

Section 4.  Construction Requirements for Conventional Projects

12-41.  CONSTRUCTION PROGRESS SCHEDULE.  A construction progress

schedule shall be prepared to monitor construction activities

from the date specified in the "notice to proceed" through the

actual project completion date.

a.  Contractor Schedule.  The contractor shall prepare a

Construction Progress Schedule (Form HUD 5372) for each

project immediately after PHA issuance of a "notice to

proceed".  The information shall be realistic and consistent

with the information provided by the general contractor on

the approved Schedule of Amounts for Contract Payments

(Form HUD 51000a).  The contractor may substitute alternate

forms (e.g., tracings) provided that all information

identified on Form HUD 5372 is included.

b.  PHA Approval.  The PHA architect shall review the general

contractor's construction progress schedule to determine

that the scheduled dates and amount of work to be completed

are reasonable and consistent with the construction contract.

If acceptable, the PHA architect shall sign the schedule and

forward it to the PHA for approval.  Upon approval by the

PHA, the approved construction progress schedule shall be

returned to the general contractor and a copy forwarded to

the AE Chief.

12-42.  SCHEDULE OF AMOUNTS FOR CONTRACT PAYMENTS.  The Schedule of

Amounts for Contract Payments (Form HUD 51000a) approved by

the Area Office is used by the PHA for making progress payments

to the general contractor.

a.  Contractor Schedule Immediately after execution of the

construction contract, the general contractor shall prepare

a Form HUD 51000a.  The completed form shall be sent to the

PHA to review and obtain Area Office approval.

b.  PHA Review.  The completed Form HUD 51000a shall be reviewed

by the PHA and the PHA architect to determine that the

scheduled work to be completed by the specified dates and

the amount of payment for such work is reasonable.  If

acceptable to the PHA, the Form HUD 51000a shall be submitted

to the Area Office.

c.  Area Office Approval.  The AE Chief shall review the Form

HUD 51000a completed by the general contractor as well as

PHA recommendations.  The AE Chief shall prepare a letter

for the Housing Director's signature advising the PHA that:

________________________________________________________________________

12-33                         10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(1)  the Form HUD 51000a is either approved as submitted or

as modified by the Area Office;

(2)  it should promptly send a copy of the approved Form

HUD 51000a to the general contractor for acceptance; and

(3)  it is authorized to make progress payments to the

general contractor in accordance with paragraph 12-43.

12-43.  CONTRACT PAYMENTS.  The PHA is responsible for making progress

payments to the general contractor based on the Schedule of

Amounts for Contract Payments (Form HUD 51000a) approved by the

Area Office.  Generally, progress payments for acceptable

work and materials delivered and stored on the site are made

at thirty (30) day intervals.

a.  Area Office Approval.  Area Office authorization of progress

payments, based on the approved Form HUD 51000a, is not

required.  However, written Area Office approval is required

before any of the monthly retainage is advanced or before

final payment is made.

b.  Contractor Request for Payment.  The general contractor

must submit a request for payment on Periodical Estimate

for Partial Payment (Form HUD 51001) for each project.  The

request shall be accompanied by the general contractor's

written designation of a certifying officer.  In addition,

the general contractor must submit the following

documentation, if applicable, with each Form HUD 51001:

(1)  Schedule of Change Orders, Form HUD 51002;

(2)  Schedule of Materials Stored, Form HUD 51003; and

(3)  Summary of Materials Stored, Form HUD 51004.

c.  PHA Approval.  The PHA shall review each general contractor

request and shall approve the advance if the following

conditions have been met:

(1)  the general contractor request is consistent with

the approved Schedule of Amounts for Contract Payments

(Form HUD 51000a);

(2)  the request does not include the amount to be retained

by the PHA pursuant to the construction contract;

________________________________________________________________________

10/80                          12-34

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(3)  the work covered by the payment has been performed in

accordance with the construction documents;

(4)  the Form HUD 51001 has been properly executed and all

applicable supporting documentation submitted; and

(5)  the general contractor has submitted all required reports

(e.g., payroll reports).

d.  Distribution of Documents.  The PHA shall retain the original

Periodical Estimate for Partial Payment (Form HUD 51001)

and any applicable supporting documentation for its project

file.  A copy of the PHA approved forms shall be sent to the

AE Chief and to the general contractor.

12-44.  PROJECT PHOTOGRAPHS.  The PHA shall periodically take photographs

to illustrate the progress of construction work.  In addition,

these photographs may be required to protect the PHA interest in

disputes relating to defective workmanship, cave-ins, or accidents.

a.  Prints.  Prints shall be at least five (5) inches by seven

(7) inches.  Each print shall be identified as follows:

(1)  project number and name;

(2)  city and state;

(3)  date photograph taken;

(4)  description of view (e.g., block, street and special

features); and

(5)  the camera position identified on a site diagram.

b.  Site Diagram.  The site diagram, prepared by the PHA

architect, shall be used to indicate camera positions.  The

diagram shall be an eight by eleven inch (8" x 11")

photo reduction of the construction contract site plan showing

the PHA architect's name, the PHA, the project number, a

graphic scale, streets, and the North point.

12-45.  SHOP DRAWINGS AND MATERIALS.  Shop drawings and material samples

shall be prepared and submitted in accordance with the agreements

reached at the construction conference.

________________________________________________________________________

12-35                          10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

a.  Contractor Submission.  The contractor is responsible for

preparing and submitting shop drawings to the PHA architect.

The contractor's letter shall list the shop drawings being

submitted and state whether the shop drawings deviate from

the approved construction documents.  Each shop drawing shall

include:

(1)  a descriptive title and drawing number;

(2)  a brief description of the work involved;

(3)  the project number and name;

(4)  the contractor's and any subcontractor's name; and

(5)  evidence of the contractor's approval.

b.  PHA Architect's Approval.  The PHA architect shall review the

shop drawings to determine whether they are consistent with

the construction documents.  The PHA architect shall require

that any corrections be made prior to approval.  upon approval,

the PHA architect shall:

(1)  sign and date each shop drawing and include the following

statement:  "This shop drawing is approved, but the

general contractor shall verify and shall be responsible

for all related documents and job conditions on the work."

(2)  send a letter to the general contractor indicating that

the shop drawing was approved and advising the contractor

that:

(a)  "This approval of the enclosed shop drawing is

general and does not relieve the contractor of the

responsibility for adherence to the contract, nor

is the contractor relieved of the responsibility

for any error which may exist", and

(b)  if applicable, "The modification shown on the

enclosed shop drawing is approved in the interest

of the PHA to effect an improvement for the project

and is ordered with the understanding that it does

not involve any change in the contract price or

time; it is subject to all contract stipulations.

and covenants; and it is without prejudice to any

and all rights of the PHA under the contract

and bond."

________________________________________________________________________

10/80                              12-36

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

c.  Distribution of Documents.  The PHA architect shall

retain a copy of the approved shop drawing, and shall

forward a copy to the general contractor and the PHA.

d.  Samples.  The general contractor shall submit certificates,

material samples, and test results to the PHA architect

for approval.  The PHA architect shall advise the general

contractor of the reasons for any disapproval and

request that another sample be submitted.  Approved

samples and data shall be retained both at the PHA

office and the project office for comparison during

construction.

12-46.  LIQUIDATED DAMAGES.  The general contractor is responsible for

completing the project within the time established in the

construction contract unless time extensions are authorized in

accordance with paragraph 12-26.  If the construction work is

not completed by the contract date, the general contractor shall

be liable for liquidated damages resulting from such unexcused

delays.

a.  Finding of Fact.  The PHA shall prepare a "finding of fact"

pursuant to paragraph 12-26 and shall submit it to the Area

Office for review and approval.

b.  Amount of Damages.  The PHA's "finding of fact" shall

identify the amount of liquidated damages to be assessed

against the general contractor and the basis used in

determining the amount.  Liquidated damages shall be

assessed at the rate established in the construction contract

and shall be withheld from any payment due the contractor.

c.  Area Office Approval.  The AE Chief, in consultation with

The Area Counsel, shall review the PHA "finding of fact"

to determine whether the contractor is responsible for the

delay and the amount of damages established by the PHA

is reasonable.  Upon completing this review, the AE Chief

shall prepare a letter for the Housing Director's signature

advising the PHA to:

(1)  send a letter to the general contractor identifying the

amount of liquidated damages being assessed and the

reasons;

(2)  send a letter to the general contractor's bonding company

identifying the amount of liquidated damages being

assessed on the general contractor; and

________________________________________________________________________

12-37                              10/80

_____________________________________________________________________

7417. 1 REV-1

________________________________________________________________________

(3)  send copies of both letters to the AE Chief.

12-47.  PARTIAL PROJECT ACCEPTANCE.  The PHA, with Area Office approval,

may accept part of a project for occupancy prior to settlement.

a.  Conditions.  The PHA may not permit early occupancy unless

the following conditions are met:

(1)  the dwelling units to be accepted (except punch list

items) have been completed and are ready for occupancy;

(2)  the general contractor agrees to early occupancy and

completion of the punch list items;

(3)  early occupancy will not inconvenience or represent a

safety risk to the occupants while the unfinished work

is being completed;

(4)  the PHA has obtained occupancy permits from

the responsible local agency for each unit to be

accepted; and

(5)  the PHA has executed an occupancy agreement with the

general contractor indicating that the PHA partially

accepts specified work provided that the contractor

accepts the responsibility to complete the project

by the established completion date.

b.  Occupancy Agreement.  The PHA shall submit the proposed

occupancy agreement to the Area Office for approval prior

to execution by the PHA.

c.  Area Office Approval.  The construction analyst shall review

the proposed occupancy agreement to determine whether

the conditions identified in subparagraph a have been

satisfied.  Upon completion of this review, the construction

analyst shall prepare a letter for the AE Chief's signature

advising the PHA of the Area Office decision:

(1)  if approvable, the letter shall:

(a)  authorize the PHA to execute the occupancy

agreement; and

(b)  request that a copy of the occupancy agreement

be submitted to the AE Chief after execution by

the PHA and the general contractor.

________________________________________________________________________

10/80                              12-38

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(2)  if not approvable, the letter shall identify the

reasons for disapproval, including the work to be

completed or corrected prior to reconsideration

by the Area Office.

12-48 thru 12-60.  RESERVED.

________________________________________________________________________

10/80

12-39 thru 12-44

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

Section  5.  Project Completion and Final Inspection

12-61.  GENERAL.  The contractor is responsible for providing the PHA

with a forty-five (45) day written notice of the expected

date by which the project will be completed and ready for

final inspection.  This section establishes the inspection

requirements which must be met prior to acceptance of completed

work and contract settlement (Section 6).

12-62.  PHA ARCHITECT'S INSPECTION.  The PHA architect shall schedule

with the contractor a date to inspect the project and prepare a

punch list of the incomplete work.

a.  Content of Punch List.  A separate punch list shall be

prepared for each building which identifies the:

(1)  date of the inspection;

(2)  name and title of the contractor representative;

(3)  each incomplete or unsatisfactory work item; and

(4)  specific location of each item of incomplete work.

b.  Contractor Notification.  The PHA architect shall send a

letter to the contractor which:

(1)  transmits a copy of the punch list;

(2)  advises the contractor to promptly correct each item

of incomplete or unsatisfactory work; and

(3)  requests that the contractor promptly notify the PHA

of the date by which the corrective work will be complete

so that the PHA can schedule a final inspection prior

to contract settlement.

c.  Deductions for Incomplete Work.  The PHA shall consult with

the PHA architect to determine if it would be advantageous

to accept a project prior to final inspection.  In such

instances, the PHA architect shall prepare a deductive

change order for Area Office approval prior to the final

inspection.  The amount of deductions from the contract

price shall be based on current replacement cost for

correcting any incomplete or unsatisfactory work.

________________________________________________________________________

12-45                            10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

12-63.  FINAL INSPECTION.  A final project inspection shall be made

when all work is completed.  Until the final inspection has been

made and approved by the Area Office, the PHA shall not advance

any of the retainage (conventional project) or make the final

payment to the contractor.

a.  Inspection Date.  Upon receipt of the contractor's notification

of the date when the corrective work will be completed,

the PHA shall schedule a final inspection.  Each member of

the inspection team shall be given a fifteen (15) day

notification of the scheduled inspection date.

b.  Inspection Participants.  The final inspection shall be

conducted by:

(1)  a PHA representative;

(2)  the PHA architect;

(3)  the AHM Chief, the AE Chief and the construction analyst;

and

(4)  a contractor representative.

c.  Inspection Conference.  The inspection team shall meet after

completing the final inspection to determine whether:

(1)  the work has been completed in accordance with the

construction documents;

(2)  there are any minor items of incomplete or unsatisfactory

work (or seasonal work such as planting of shrubs

and lawns) and reach agreement on the items to be

included on the PHA architect's final punch list; or

(3)  there are any major deficiencies which must be corrected

by the contractor so that another final inspection can

be made prior to contract settlement.

d.  Inspection Report.  The PHA architect shall prepare a final

inspection report and certificate of completion based on

the agreements reached at the inspection conference.  The

certificate of completion will show the amount of payment

to be withheld for any incomplete work provided that such

work is not of a major nature requiring correction before

settlement.

________________________________________________________________________

10/80                           12-46

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

e.  Area Office Approval.  The PHA shall submit a copy of the

PHA architect's final inspection report and the proposed

certificate of completion to the Area Office for approval.

The AE Chief shall review the PHA submission to determine

that the final inspection report is acceptable and, if

applicable, any amount to be withheld is sufficient to complete

the corrective work.  If approvable, the AE Chief shall

prepare a letter for the Housing Director's signature

authorizing the PHA to accept the project and prepare for

settlement.

12-64 thru 12-70.  RESERVED.

________________________________________________________________________

12-47 thru 12-54                        10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

Section 6.  Contract Settlement

12-71.  GENERAL.  The PHA, upon receipt of written authorization from the

Area Office, shall notify the contractor to prepare for settlement.

The PHA shall also advise the contractor to submit the

documentation identified in this section for PHA and Area Office

approval prior to settlement.

12-72.  SETTLEMENT DOCUMENTS.  The contractor is responsible for preparing

and submitting the following to the PHA:

a.  Conventional and Turnkey Projects.  The following documents

are required for all projects, whether developed under the

conventional or turnkey method.

(1)  a certificate of occupancy issued by the responsible

local agency for each building;

(2)  two notarized originals of the contractor's release

and certification which indicates:

(a)  the work was completed in accordance with the

construction documents (including change orders)

except any minor items identified on the

PHA architect's final inspection report;

(b)  the total amount due the contractor and a

separately stated amount for each unsettled

claim against the PHA;

(c)  the PHA is released of all claims, other than

those stated in the contractor's release; and

(d)  wages paid to laborers or mechanics were

consistent with the wage rate requirements

of the contract, and there are no

outstanding claims for unpaid wages.

(3)  an assignment of all guarantees and warranties to the PHA.

b.  Conventional Projects.  In addition to the documents

identified in paragraph a, the general contractor shall submit

a "final"  Periodical Estimate for Partial Payment (Form

HUD 51001).

________________________________________________________________________

12-55                             10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

c.  Turnkey Projects.  In addition to the documents identified

in subparagraph a, the turnkey developer Shall submit the

following:

(1) the as-built drawings (paragraph 12-23);

(2) a copy of the receipt for real property taxes paid by

the developer during the construction period;

(3) the title binder, evidencing that good and marketable

title will be conveyed to the PHA; and

(4) a copy of the proposed deed.

12-73.  PHA CONTRACT SETTLEMENT REPORT.  The PHA in consultation with

the PHA architect and attorney shall review the contractor's

settlement documents and prepare a report on its findings.

a.  PHA Review.  The PHA shall review the construction documents,

the PHA records, and completed work, to determine whether

the contractor's statements concerning compliance with the

construction documents (including change orders) and identified

work to be completed are accurate.

b.  PHA Report.  Upon completing its review, the PHA shall prepare

a contract settlement report indicating PHA agreement

with the contractor's statements.  The PHA report shall

also identify:

(1)  the current status of any incomplete or seasonal work;

(2)  any outstanding disputes or claims;

(3)  any PHA exceptions to the contractor's settlement

documents; and

(4)  the PHA attorney statement as to the adequacy of the

proposed deed and title information (turnkey projects

only).

c.  Certificate of Completion.  The PHA or PHA architect shall

prepare the proposed certificate of completion in the form

prescribed by the Area Office.

________________________________________________________________________

10/80                              12-56

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

d.  PHA Submission  The PHA shall submit a copy of the following

to the Area Office for approval:

(1)  all settlement documents identified in paragraph 12-72

for the applicable development method;

(2)  the PHA contract settlement report; and

(3)  the proposed certificate of completion.

12-74.  AREA OFFICE REVIEW.  The AE Chief is responsible for coordinating

the review and recommending approval of the certificate of

completion.

a.  Standard Processing Time.  The standard processing time (SPT)

is the number of calendar days from receipt of the settlement

documents and certificate of completion by the PCR Unit and

a decision by the Housing Director.  The SPT for Area Office

review and approval (or disapproval) of the certificate of

completion is ten (10) calendar days.

b.  AE Branch.  The AE Chief in order to recommend approval must

determine that:

(1)  all work has been completed in accordance with the

construction documents;

(2)  the proposed certificate of completion is acceptable;

and

(3)  the amount to be withheld from the contractor is

sufficient to complete any items on the PHA architect's

punch list, including seasonal work.

c.  Legal Division.  The Area Counsel, in order to recommend

approval, must determine and advise the AE Chief that:

(1)  the contractor's release and certification is consistent

with the terms of the contract;

(2)  for turnkey projects, the proposed deed and title

information is acceptable and are consistent with

the contract of sale; and

(3)  for turnkey projects, the scheduled closing date.

________________________________________________________________________

12-57                            10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

d.  Labor Relations Staff.  The Labor Relations Staff,

in order to recommend approval, must determine and advise

the AE Chief that the contractor's wage certification is

acceptable.

e.  PHA Notification.  The AE Chief, upon determining that the

contract settlement documents are in order, must sign the

certificate of completion and submit it for the

Housing Director's signature.  The original shall be

promptly sent to the PHA.  If applicable, the PHA and

turnkey developer shall be advised of the scheduled closing

date.

12-75.  PAYMENT OF CONTRACTOR.  The PHA upon receipt of the approved

certificate of completion is authorized to make payment to the

contractor of the amounts approved by the Area Office.  For

turnkey projects, payment shall be made at the closing of the

sale.

a.  Contract Payment.  The PHA payment to the contractor shall

be the amount specified in the certificate of completion

approved by the Area Office and shall not include any amount

to be retained for:

(1)  warranty retainage or disputed items; and

(2)  incomplete work, such as punch list or seasonal

items.

b.  Final Payments.  The PHA is not authorized to make final

payment of any amounts withheld without prior Area Office

approval.  When punch list or seasonal work items are

completed, the PHA shall submit a revised certificate of

completion for Area Office approval.

12-76.  TURNKEY CLOSING PROCEDURES.  The closing for turnkey projects

shall take place in accordance with the following requirements:

a.  Title Insurance.  The PHA must obtain a title insurance

policy, or other title guarantee acceptable to the Area

Office, at closing.  The title policy shall guarantee

that title is good and marketable and is free of any

mortgage, lease, lien or other encumbrances, such as use

or building restrictions, zoning ordinances, easements

or rights-of way which would affect the value or proposed

use of the site.  In those instances where several

contiguous parcels are being acquired, a blanket title

insurance policy should be obtained for the entire site.

________________________________________________________________________

10/80                               12-58

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

b.  Curing Title Defects.  The PHA attorney shall ensure that

any outstanding mortgages, leases, or liens have been cleared.

c.  Settlement Record.  The closing details for each transaction

shall be recorded in triplicate on the Real Estate Settlement

Record (Form HUD 51975) or a similar locally used and accepted

settlement record.

d.  Deed Recordation.  The PHA shall ensure that the deed is

promptly recorded by its attorney.

e.  Declaration of Trust.  The PHA shall execute and record the

Declaration of Trust (Form HUD 52190) prepared by the Area

Counsel.  A copy of the executed Declaration of Trust shall

be returned to the Area Office as soon as it has been

recorded.

12-77.  WARRANTY INSPECTIONS.  The PHA is responsible for performing

required warranty inspections during the warranty period and

promptly notifying the contractor in writing to remedy any

defects.

a.  Applicability.  These requirements apply to projects developed

under either the conventional or turnkey method and include:

(1)  manufacturer or contractor warranties on equipment

and systems; and

(2)  contractor warranty on materials and workmanship.

b.  Contractor Responsibility.  The contractor, upon receipt

of PHA written notice, shall promptly remedy any

defects due to the use of faulty equipment or materials, or

poor workmanship.  The contractor is also responsible for

paying for any damage to other work resulting from such

defects.

c.  Warranty Period.  The warranty period for all construction

work shall be at least 365 calendar days from the date

specified on the certificate of completion that is

applicable to the work in question or such longer period

otherwise specified in the construction contract.

d.  PHA Inspection.  The PHA shall inspect each dwelling unit

at least every three months during the warranty period.

If any deficiencies are noted, the PHA shall take prompt

action to protect its rights under the applicable warranty.

________________________________________________________________________

12-59                            10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

e.  Final Inspection.  The PHA shall schedule a final warranty

inspection prior to the expiration of the one-year warranty

period.  The final inspection shall be performed by the PHA,

the PHA architect, and the AE Chief and the AHM Chief to

determine whether there are any deficiencies and whether such

deficiencies are the responsibility of the PHA or contractor.

12-78 thru 12-90.  RESERVED.

________________________________________________________________________

10/80                  12-60 thru 12-66

_____________________________________________________________________

7417.1 REV-1 CHG-6

________________________________________________________________________

Section 7.  Date of Full Availability

12-91.  DEFINITION.  The date of full availability (DOFA) is the last day

of the month in which all housing units in a project are available

for occupancy.  A unit is considered available if an occupancy

certificate has been obtained from the responsible local agency.

It is not necessary for the purpose of establishing DOFA that

construction work such as landscaping and punch list items be

completed.

a.  Turnkey Projects.  DOFA shall be established as the last day of

the month in which settlement takes place.

b.  Conventional Projects.  DOFA shall be established as the last

day of the month in which substantially all units (e.g., 95

percent) are available for occupancy.

c.  Acquisition Projects.  DOFA shall be established as the last

day of the month in which settlement takes place.  For

scattered site projects, DOFA shall be established as the last

day of the month in which substantially all the units (e.g., 95

percent) have been acquired by the PHA.

12-92.  PHA REPORTING.  The PHA is responsible for notifying the Field

Office when DOFA is achieved.  It is critical that the PHA report

DOFA promptly, since DOFA establishes the date on which interest

*  stops accruing toward the development cost of the project and     *

serves as the basis for determining the End of the Initial

Operating Period.

*  a.  PHA Submission.  The PHA shall submit for Field Office approval

two signed originals of the Notice of Date of Full Availability

(Form HUD-52423).

b.  Delinquent PHA Submission.  The construction analyst shall

periodically determine if there is any project, based on

occupancy agreements or construction progress reports, for

which DOFA has not been but should have been reported by the

PHA.  If applicable, the construction analyst shall prepare a

letter for the Housing Development Division Director's

signature advising the PHA that:

(1)  it appears, based on Field Office records, that DOFA has

been achieved;

(2)  if DOFA has been achieved, the PHA must submit the

documents identified in subparagraph a within thirty (30)

calendar days of the date of the Housing Development

Division Director's letter;

________________________________________________________________________

12-67                      10/88

_____________________________________________________________________

7417.1 REV-1 CHG-6

________________________________________________________________________

(3)  if DOFA has not been achieved, the PHA must submit an

explanation of the reasons for delay within thirty (30)

calendar days of the date of the Housing Development

Division Director's letter; and

(4)  if the required information is not received by the thirty

(30) day deadline date, the Field Office will prepare and

execute the Form HUD-52423.

12-93.  FIELD OFFICE REVIEW.  The construction analyst shall review the PHA

submission (including delinquent submissions) to verify that

substantially all housing units were satisfactorily completed and

were available for occupancy on the date established by the PHA.

a.  Approval.  If the DOFA date is approvable, the construction

analyst shall prepare a letter, for the Housing Development

Division Director's signature transmitting a copy of the

approved Notice of Date of Full Availability (Form HUD-52423)

signed by the Housing Development Division Director.  A copy of

the signed Form HUD-52423 shall be sent to the AHM Chief, the

Mortgage Credit Chief, the Regional Financial Management

Specialist, and the Assistant Secretary for Administration

(Attention:  Office of Finance and Accounting).

b.  Disapproval.  If the DOFA date is not approvable, the

construction analyst shall prepare a letter for the Housing

Development Division Director's signature indicating that the

Form HUD-52423 was not approved, the reasons for disapproval,

and conditions which the PHA must meet before submitting a

revised Form HUD-52423 to the Field Office.

c.  Unusual Conditions.  The construction analyst, in consultation

with the designated MHR and Mortgage Credit Chief, shall review

any PHA submissions which indicate that DOFA will be delayed

because of unusual circumstances.  For example, the PHA may be

experiencing difficulty in obtaining bids for rehabilitation of

scattered site housing or existing housing may not be available

to permit timely achievement of DOFA.  In such instances,

consideration shall be given to establish a separate project

for all units that have been completed and to issue a Form

HUD-52423 for those units that have been acquired and are

available for occupancy.  This action is necessary to stop the

accrual of interest and minimize the amount of the initial

operating deficit charged to the development cost of the

project.

12-94 thru 12-100.  RESERVED.

________________________________________________________________________

10/88                         12-68 thru 12-74

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

Section 8.  End of Initial Operating Period

12-101. DEFINITION.  The end of the initial operating period (EIOP)

is the last day of the first calendar quarter (March, June,

September, December) after DOFA, provided that ninety-five (95)

percent of the units are occupied.  However, if ninety-five (95)

percent occupancy is not achieved, EIOP is automatically

established as the last day of the second calendar quarter after

DOFA.

12-102. PHA REPORTING.  The PHA is responsible for promptly notifying

the Area Office of the EIOP date.  It is critical that the PHA

report EIOP promptly, since EIOP establishes the day that the

project is eligible for operating subsidies.

a.  Determination of Date.  The PHA shall determine EIOP in

accordance with the following examples that are based on

the assumption that DOFA was established on November 30, 1980.

(1)  Example 1.  Ninety-five (95) percent occupancy is achieved

on February 10, 1981.  In this example EIOP would be

established as march 31, 1981 -- the end of the first

calendar quarter after DOFA.

(2)  Example 2.  Ninety-five (95) percent occupancy is not

achieved by March 31, 1981 -- the end of the first

calendar quarter.  In this example, EIOP would

automatically be established as June 30, 1981 -- the end

of the second calendar quarter after DOFA.

b.  PHA Submission.  As soon as EIOP is determined, the PHA

shall submit two signed originals of the Notice of End of

Initial Operating Period (Form HUD 52344) to the Area Office.

c.  Delinquent PHA Submission.  The AHM Chief shall determine

at the end of each calendar quarter if there are any projects

that have achieved DOFA for which EIOP has not been reported

by the PHA.  If applicable, the AHM Chief shall prepare a

letter for the Housing Director's signature advising the

PHA that:

(1)  the first calendar quarter has passed and the PHA

has not reported EIOP;

________________________________________________________________________

12-75                             10/80

_____________________________________________________________________

7417.1 REV-1

________________________________________________________________________

(2)  the Area Office has prepared a Notice of End of

Initial Operating Period (Form HUD 52344) which must

be signed by the PHA and returned to the Area Office

within (30) calendar days of the date of the Housing

Director's letter; and

(3)  if the signed Form HUD 52344 is not returned by the

thirty (30) day deadline date, the Area Office will

execute it on behalf of the PHA.

12-103. AREA OFFICE REVIEW.  The AHM Chief shall review the PHA submission

(including delinquent submissions).  If approvable, the

AHM Chief shall sign the Form HUD 52344 and return it to the PHA.

Otherwise, the AHM Chief shall contact the PHA to ascertain

the correct date.  A copy of the signed Form HUD 52423 shall

also be sent to the Mortgage Credit Chief, the Regional Financial

Management Specialist, and the Assistant Secretary for

Administration (Attention:  Office of Finance and Accounting).

12-104 thru 12-110.  RESERVED

________________________________________________________________________

10/80                        12-76 thru 12-80

_____________________________________________________________________

7417.1 REV-1 CHG 3

________________________________________________________________________

Section 9.  Actual Development Cost

12-111.  PHA REPORTING.  The PHA is responsible for promptly notifying

the Area Office when all project development activities are

completed and the PHA has made payment for all obligations

incurred in the development of a public housing project..

a.  Reporting Date.  The PHA shall submit its report as soon

as the actual development cost for the project is known.

However, unless written Area Office authorization is

obtained, the PHA report shall be submitted within

*       twenty-four (24) months after DOFA.  PHA requests for an     *

extension shall be accompanied by a detailed explanation of

the reasons that are beyond PHA control (e.g., litigation

unresolved disputes, pending claims), justifying Area

Office approval of an extension.

b.  PHA ADCC Submission.  The PHA upon determining the actual

development cost for a specific public housing project

shall submit the following for Area Office approval:

(1)  Actual Development Cost Certificate (ADCC),

Form HUD-52427;

(2)  a copy of an Independent Public Accountant (IPA)

audit including comments on the ADCC;

(3)  Statement of Actual Development Cost prepared on

*            Form HUD-52484 (Development Cost Budget/Cost            *

Statement); and

(4)  if applicable, a detailed explanation of any actual

costs incurred that exceed the amount for any

development cost account (total) of the latest Area

Office approved development cost budget on Form

HUD-52484.

12-112.  AREA OFFICE MONITORING.  The Mortgage Credit Chief is

responsible for ensuring the timely development close-out of all

public housing projects.

a.  Control Record.  The Mortgage Credit Chief shall

establish a control record for all projects reaching

DOFA so that:

________________________________________________________________________

12-81                       7/82

HUD-Wash., D. C.

_____________________________________________________________________

7417.1 REV-1 CHG 3

________________________________________________________________________

*            (1)  each PHA shall be notified one year after DOFA to be *

prepared for an IPA audit and arrange for submission

of the ADCC by the deadline date;

*            (2)  the Assisted Housing Management (AHM) Branch shall be

notified to incorporate the project's costs in the

regularly scheduled biennial IPA audit.  If the

project's costs cannot practicably be incorporated in

the regularly scheduled biennial IPA audit, then a

separate audit for purposes of the ADCC shall be

arranged to be completed in sufficient time to permit

the ADCC to be submitted within the deadline.  The

cost of such an audit shall be included in the

development cost for the project;                 *

(3)  the Regional Inspector General for Audit (RIGA) shall

be advised of all overdue ADCCs so that IPA audits

may be rejected if they fail to address ADCC audits

(see Handbooks in the 7476 series);

*            (4)  in those instances where the IPA auditor indicates

to the RIGA that it will not be possible to make a

final determination of Actual Development Cost for

purposes of the ADCC, the RIGA shall notify the

Housing Director.  For projects that cannot be

audited, the Housing Director is responsible for

determining how many and which personnel will be

detailed to establish the actual TDC cost using the

actual cost in the latest approved development cost

budget, the funds advanced and the Housing Agency's

records of expenditures.  The Housing Director is to

submit to the Area Office Manager for approval a

written recommendation of the amount to become the

actual development cost for each such project.  If

the Area Office Manager does not agree with the

recommendation, the Regional Administrator is to be

advised.  The Regional Administrator shall determine

whether or not Regional assistance can be provided.  If

the Regional Administrator determines it appropriate,

Headquarters guidance and/or assistance shall be

requested; and                                   *

(5)  close-out actions for each project shall be closely

monitored and a quarterly report transmitted to the

Regional Project Financing Specialist and RIGA on all

projects that have achieved DOFA but ADCCs have not

been approved by the Area Office.

________________________________________________________________________

7/82                             12-82

_____________________________________________________________________

7417.1 REV-1 CHG 3

________________________________________________________________________

b.  Delinquent ADCC Submission.  Where a PHA has not submitted

an ADCC by the deadline date and has not requested an

extension, the Mortgage Credit Chief shall prepare a letter

for the Housing Director's signature advising the PHA that:

(1)  the PHA has not submitted the ADCC by the required

date;

(2)  the PHA must submit the documents identified in

subparagraph 12-111 within sixty (60) days or must submit

documentation justifying Area Office approval for an

extension within thirty (30) days;

(3)  the PHA is not authorized to make payment after the

date of the Housing Director's letter for any PHA

obligations with respect to the project without

prior written Area Office approval;

(4)  PHA requests to make payments must be accompanied by

a current Development Cost Budget (Form HUD-52484)

and an IPA audit;

*           (5)  in the event that the PHA fails to submit the budget

and audit, the Area Office shall arrange for the IPA

audit and shall charge it to the development cost for

the project; and

(6)  if the documentation required by paragraph 12-111 is

not received within sixty (60) days or by the approved

extended date, the Area Office will use the development

costs (actual and committed) identified on the latest

approved Development Cost Budget/Cost Statement, Form

HUD-52484, as the basis for amending the ACC, the

Permanent Note, the Development Cost Budget and

approval of the ADCC and shall notify the PHA in

writing.                                           *

12-113.  AREA OFFICE REVIEW.  Each PHA submission shall be reviewed to

determine that it is acceptable.

*       a.  Mortgage Credit Branch.  In order to recommend approval

of the Statement of Actual Development Cost and the ADCC,

the Mortgage Credit Chief must determine that:        *

________________________________________________________________________

12-83                          7/82

_____________________________________________________________________

7417.1 REV-1 CHG 3

________________________________________________________________________

(1)  the actual costs incurred for each development

account (totals), do not exceed the amounts

identified on the latest Area Office approved

development cost budget, Form HUD-52484, and do not

exceed the amount of advances authorized by the

Area Office;

(2)  all disputed, contingent or unliquidated items have

been satisfied;

(3)  the amounts identified in Accounts 1450 thru 1475

are consistent with the construction documents

(including change orders);

(4)  there is a zero entry for contract work in progress

(Account 1480); and

*           (5)  if applicable, the PHA's explanation of cost overruns

for each account justifies Area Office approval

but does not exceed the approved estimated TDC

specified in the ACC.

b.  AHM Branch.

(1)  in order to recommend approval of the ADCC, the AHM

Chief must determine that no development deficiencies

have been identified in the initial engineering

survey, in accordance with the procedures set forth

in the Project Management Handbook RHM 7460.1 SUPP 1,

or in subsequent operations which have not been

corrected.  Development deficiencies are deficiencies

in a project that relate to errors or inadequacies

in the design or construction of a project which

become known before approval of the ADCC.  Design

deficiencies result from the use of plans and

specifications that fail to meet HUD and other

applicable design standards in effect at the time

of project approval.  Construction deficiencies

result from the use of improper construction methods

or materials, poor workmanship, or failure to complete

the project in accordance with HUD-approved plans.

(2)  If the AHM Chief determines that there are uncorrected

development deficiencies, the AHM Chief shall not

recommend approval of the ADCC and shall provide to

the Chiefs, Multifamily Housing Programs, AE, and

Mortgage Credit, a written description of the

deficiencies and related cost estimates.  Upon

correction of the deficiencies, the AHM Chief shall

recommend approval.                                *

________________________________________________________________________

7/12                              12-84

_____________________________________________________________________

7417.1 REV-1 CHG 3

________________________________________________________________________

*       c.  Area Office Approval.  If the Statement of Actual

Development Cost and the ADCC are approvable, the

Mortgage Credit Chief shall recommend approval by signing

both documents, the AHM Chief shall recommend approval

by signing the ADCC; and the Housing Director shall

approve the ADCC and Statement of Actual Development

Cost by signing both documents.

d.  PHA Notification.  The Mortgage Credit Chief shall

prepare a letter for the Housing Director's signature

transmitting the approved ADCC and Statement of Actual

Development Cost to the PHA.  The letter shall also

instruct the PHA to:

(1)  if the project has been permanently financed through

the sale of bonds, deposit any excess development

funds in the advance amortization fund;

(2)  if the project has not been permanently financed

through the sale of bonds, send any excess funds to

the Assisted Housing Accounting Division, OFA, in

Headquarters for application against outstanding

financing and:

(a)  the PHA is not authorized to use these funds

for any purposes; and

(b)  the Area Office will forward an amended ACC and

Permanent Note for PHA execution to reflect the

TDC amount identified on the ADCC.

e.  ACC and Permanent Note Amendments.  If the amount in the

approved ADCC differs from the TDC specified in the ACC

and the project is not permanently financed by bonds, the

Mortgage Credit Chief shall initiate amendments to the

ACC and the Permanent Note and either reserve additional

or recapture excess development funds.  If the project

is permanently financed by bonds, the procedure is the

same except Permanent Notes are not required.  In no

event shall the reserved funds be reduced for an amount

less than the amount required to pay the debt service on

the outstanding bonds.  The current and appropriate AC

rate is used for the entire amount of the development

cost.                                                   *

________________________________________________________________________

12-85                       7/82

_____________________________________________________________________

7417.1 REV-1 CHG 3

________________________________________________________________________

*           (1)  When additional funds are required the PCR Supervisor

shall be requested to prepare a Project Accounting

Data (HUD-52540) and a notification letter shall be

signed by the Area Manager and processed by the

Regional Accounting Director.  The Area Counsel

shall be requested to prepare an amended ACC and a

revised Permanent Note based on the approved ADCC

(a revised Permanent Note is issued only when the

project was not financed by New Housing Agency

Bonds).  The amended ACC and Permanent Note shall be

forwarded to the PHA simultaneously for execution.

Upon receipt of the amended ADCC and Permanent Note

executed by the PHA, the Housing Director shall

execute them for HUD.

(2)  When it is necessary to recapture excess funds, the

Area Counsel shall be requested to prepare an amended

ACC and a revised Permanent Note based on the approved

ADCC (a revised Permanent Note is issued only when

the project was not financed by New Housing Agency

Bonds).  The amended ACC and Permanent Note shall be

forwarded to the PHA simultaneously for execution.

Upon receipt of the amended ACC and Permanent Note

executed by the PHA, the Housing Director shall

execute them for HUD.  The PCR Supervisor shall then

be requested to prepare a Project Accounting Data

(HUD-52540) for the Area Manager's signature.  The

Form HUD-52540 and a copy of the amended ACC shall

be transmitted to the Regional Accounting Director

for processing.

f.  Distribution of Documents.  The distribution of these

documents should be made in accordance with Chapter 7,

paragraph 7-115(b).

g.  Incurring Additional Obligations.  After HUD approval of

the ADCC, PHAs are prohibited from incurring additional

obligations of development funds without the prior written

approval of the Assistant Secretary for Housing.  Approval

will be given in writing and a copy will be sent to the

Office of Finance and Accounting.  In the event additional

development work is approved, the PHA shall be instructed

to submit revised Forms HUD-52427 and HUD-52484 (Statement

of Actual Development Cost) when work is completed.  The

same general procedures as set forth in this Section

shall pertain to the processing of the revised forms. *

________________________________________________________________________

7/82                                  12-86