SPECIAL PERMITS APPLICATION FORM

INFORMATION COLLECTION PROCESS

TIMELINE

Day 1:				Drafting of form and 60-day Federal Register (FR) Notice

begins; confer with Bureau of Transportation Statistics (BTS) regarding form

Day 30:			Finalize form and 60-day FR Notice

Day 30-45:			Coordination, approval of 60-day FR Notice

Day 52:			Publish 60-day FR Notice

Day 52-112:			60-day comment period

Day 112-122:			Consider comments; update Information Collection (IC)

package

Day 129:			Complete revised form

Day 130:	IC package, including revised form to OST for review, approval

Day 144:  			OST review complete

Day 151-158: 			Update package to incorporate OST comments

Day 158:			Finalize 30-day FR Notice

Day 158-172:			Coordination, approval of 30-day FR Notice

Day 179:			Publish 30-day FR Notice

Day 179-209:			30-day comment period

Day 209-219:			Consider comments, update IC package

Day 226:			Complete revised form

Day 227:                                  IC package, including revised form to OMB for review

Day 227-287:			60-day OMB review

Day 287: 			OMB approval

Day 287 - 297: 		Update website with form