|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| |  |  | | --- | --- | |  |  | | **Plan G3.C1.P6 Hoosier Training Association "Learn to Earn" (Project LTE)** | | |  | | | **Plan Source:** | 2001 Annual Report | | **Goal 3:** | Economic Opportunity | | **Category 1:** | Workforce Development | | **Plan 6:** | Hoosier Training Association "Learn to Earn" (Project LTE) | |

|  |  |  |
| --- | --- | --- |
|  |  |  |
| |  |  | | --- | --- | |  |  | | ***I. Baseline*** | | | Program/Project Description: | Industry-based training programs are needed in order to train EZ residents with skill sets required by area industries. | | Baseline: | There are a limited number of job skills training programs currently in existence for Zone residents to prepare them for careers within the healthcare industry and become self sufficient. | | Proposed Outcome: | Provide Zone residents with job training and employment opportunities within the healthcare industry. | | HHS EZ Funds(Round I): | $0.00 | | HUD EZ Funds(Round II): | $50,000.00 | | Amount of HUD Round II EZ grant under contract/agreement with third party: $0.00 | | | Non-EZ/EC Grant Funds: | $53,400.00 | | Total Budget: | $103,400.00 | | Plan Status: | Active | | Review Status: | Approved | |

|  |  |  |
| --- | --- | --- |
|  |  |  |
| |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | |  |  |  |  |  |  |  | | ***II. Sources of Program Funds*** | | | | | | | | A. | HHS EZ Funds (Round I): | | | $0.00 | | | | B. | HUD EZ Funds (Round II): | | | $50,000.00 | | | |  | Amount of HUD Round II EZ grant under contract/agreement with third party: | | | | | $0.00 | | C. | Non-EZ/EC Grant Funds: | | | $53,400.00 | | | |  | **Participating Entity (Non EZ/EC Grant Funds)** | | | **Private** | **Cash** | **In-Kind** | |  | 1. | CDBG |  | No | $53,400.00 | $0.00 | |  | **Total** | |  | | **$53,400.00** | **$0.00** | |

|  |  |  |
| --- | --- | --- |
|  |  |  |
| |  |  |  |  | | --- | --- | --- | --- | |  |  |  |  | | ***III. Uses of Program Funds*** | | | | | **Lead Implementing Entity** | | | **Amount** | | A. | Hoosier Training Program |  | $103,400.00 | | **Total** | | | **$103,400.00** | |

|  |  |  |
| --- | --- | --- |
|  |  |  |
| |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | |  |  |  |  |  |  |  | | ***IV. Status of Projected Milestones*** | | | | | | | |  | | | **P r o j e c t e d** | | **% Complete as of** | | | **Milestones** | | | **Start** | **End** | **07/01/2000** | **06/30/2001** | | A. | Recruit EZ residents |  | 01/04/1999 | 10/31/2001 | 100 | 100 | | B. | Identify and hire instructors |  | 01/04/1999 | 12/29/2001 | 100 | 100 | | C. | Start home healthcare training program |  | 02/01/1999 | 10/31/2001 | 100 | 100 | | D. | Develop partnerships with healthcare employers for on-the-job training (practicums) and employment of graduating trainees. |  | 02/01/1999 | 10/31/2001 | 50 | 75 | | E. | Coordinate hiring activities with partnering employers for graduating trainees. |  | 05/10/1999 | 10/31/2001 | 50 | 75 | | F. | Conduct post-employment case management for EZ residents securing full-time employment. |  | 05/10/1999 | 12/31/2002 | 50 | 50 | |

|  |  |  |
| --- | --- | --- |
|  |  |  |
| |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | |  |  |  |  |  |  | | ***V. Progress Towards Projected Outputs*** | | | | | | | **Outputs** | | | | **Projected** | **To Date** | | A. | Job Training | | | | | |  | 1. | Number of job training programs |  | 1 | 1 | |  | 2. | Number of EZ/EC residents trained |  | 90 | 32 | |  | 3. | Number of EZ/EC resident trainees placed in jobs |  | 65 | 24 | | B. | Job Match | | | | | | C. | Job Fairs | | | | | | D. | Other Workforce Development Programs | | | | | | E. | Other unique output measurement: | | | | | |  | 1. | Maintain 70% employment retention rate of employed Hoosier graduates. |  | 45 | 23 | | **Percentage of outputs benefiting EZ/EC Residents** | | | | **100%** | **100%** | |

|  |  |
| --- | --- |
|  |  |
|