Change Request

Information Collection #5, 	“Test of Effectiveness of Screening Recruitment Messages among African American Women in North Carolina”

Previously Approved: November 14, 2011

http://www.reginfo.gov/public/do/PRAViewIC?ref_nbr=200906-0920-015&icID=200111

Reference:	“Focus Group Testing to Effectively Plan and Tailor Cancer Prevention and Control Communication Campaigns”

OMB No. 0920-0800 (generic)

The generic clearance was originally approved for three years, with an expiration date of 1/31/2012.  An Extension request was processed in 2011.  The new expiration date for the generic clearance is 11/30/2014.

Change Requested:	Reschedule data collection period for IC #5

From: 	2011

To:	January - July 2012

There are no changes to the approved project objectives, the data collection instruments, or data collection procedures. The proposed change will not affect the estimated burden to respondents.

Justification:	CDC’s original plan was to conduct Information Collection #5 in 2011, however, due to delays, OMB approval was not obtained until 11/14/2011.  CDC reviewed the project timeline and determined that conducting the information collection during the late November/December timeframe was infeasible.  CDC requests OMB approval to reschedule data collection for early 2012.