Attachment 3

Gss Schedule

2011 GSS Schedule

| Deliverable / Milestone | Contract Date | Due Date |
| --- | --- | --- |
| E-mail previous survey cycle school coordinators to confirm that they would again serve in that role and to verify contact information. | By 1st week in October | 10/07/2011 |
| E-mail school coordinators to announce the opening of data collection and provide Web survey hyperlink, user name, and password. Federal Express package of survey materials sent to school coordinators. | By October 31st | 10/31/2011 |
| E-mail school coordinators who have not yet completed Part I to prompt them to do so by deadline. | Mid-November | 11/18/2011 |
| GSS Part I due date | November 30 | 12/02/ 2011 |
| Contact school coordinators who have not submitted Part I. E-mail prompt for those who have logged in to the Web survey system. Telephone prompt for those who have not. | 1st week in December | 12/05/2011 |
| E-mail school coordinators who had not yet submitted Part I to remind them of February 28, Part II deadline. | January 31st | 1/27/2012 |
| Letter to school coordinators reminding them of February 28, Part II due date. | mid-February | N/A |
| GSS Part II due date. | February 28th | 2/29/2012 |
| E-mail school coordinators who have not yet submitted Part II to prompt them to do so. | 1st week in March | 3/05/2012 |
| E-mail to school coordinators about president’s letter for schools less than 50% complete. For schools 50% or more complete, send an e-mail prompting them to complete the survey. | By March 31 | 3/30/2010 |
| Federal Express letter about the president’s letter to school coordinators who had less than 50% of the units submitted. For schools with 50% or more complete, send a letter prompting them to complete the survey. | By 1st week in April (one week after initial e-mail) | 4/06/2012 |
| Federal Express letter to presidents of institutions that have Less than 50% of the units submitted; copy sent to school coordinator. | 3rd week in April (2 weeks after FedEx notification) | 4/20/2012 |
| Send thank you e-mail to school coordinators who have submitted Part II. | 1st week in May | 5/04/2012 |
| NSF thank-you letter sent to presidents of institutions that completed the GSS; copy sent to school coordinator. | Mid to late May | 5/18/2012 |
| Close-out data collection for the survey cycle | End of May | 5/31/2012 |
| Data editing completed | June | 6/29/2012 |
| Data imputations completed | July | 7/31/2012 |
| Final edited, imputed data file delivered to NSF | August | 8/31/2012 |
| Public Use data file completed | September | 9/28/2012 |
| Methodology report | Within 3 months after final data file delivery | 11/30/2012 |
| Data Release Info Brief | 2 weeks after final data file delivery | 10/14/2012 |
| Graduate Students and Postdoctorates in Science and Engineering Detailed Statistical Tables (DSTs), tables shells and population data tables | 2 months after final data file | 10/31/2012 |
| NIH-specified Statistical Tables and Figures | 10 weeks after final data delivery | 11/9/2012 |
| Academic Institutional Profiles tables | 3 months after final data delivery | 11/30/2012 |