**Attachment 4: GSS Schedule**

|  |  |  |
| --- | --- | --- |
| **Deliverable/Milestone** | **Due Date** | **Proposed Date** |
| **Tasks 3, 4, 5, 6 Conduct GSS (for 2014, 2015, 2016, and 2017 survey cycles)**  |
| Revised Survey Operations Plan | 3 month prior to survey launch date | July, 2014-17 |
| Survey Instrument Update | October 15th | September, 2014-17  |
| Survey Launch | End of October | October 15, 2014-17 |
| GSS Part I Due Date | Mid-December | November 30, 2014-17 |
| GSS Part II Due Date | End of February | February 28, 2015-18 |
| Survey Close-out  | End of May | April 30, 2015-18 |
| Data Editing  | End of June | May 15, 2015-18 |
| Data Imputation | End of July | June 30, 2015-18 |
| Data Files |  |  |
| Final Edited, Imputed Data File | End of August | July 15, 2015-18 |
| WebCASPAR Input | End of September | July 15, 2015-18 |
| Public Use Data Files | End of September | August 30, 2015-18 |
| NCSES Data Repository Files  | Within 1 month of data release | December, 2015-18 |
| Methodology report | Within 3 months after final data file | September 30, 2015-18 |
| **Task 7 Conduct FFRDC Postdoc Survey**  |
| Survey Instrument Update | End of September | September, 2015 & 2017 |
| Survey Launch | End of October | October, 2015 & 2017 |
| Survey Close-out  | End of December | December, 2015 & 2017 |
| FFRDC postdoc data files and draft report | Within 4 weeks after end of data collection | January, 2016 & 2018 |
| NCSES Data Repository Files  | Within 1 month of data release | April, 2016 & 2018 |
|  **Task 8 Publications and Data Dissemination (for each survey cycle)** |
| Draft Data Release Info Brief Concept | 2 weeks after final data file | July 15, 2015-18 |
| Draft Data Release Info Brief | 2 weeks after NSF concept approval | August 15, 2015-18 |
| Detailed Statistical Tables (DSTs) Shells, Populated DSTs and Technical Appendices | 2 month after final data file | 1st draft: July 15, 2015-18 |
| Supplemental DSTs (e-Tables) | 1 month after DSTs release | 1st draft: August 15, 2015-18 |
| Survey Overview Update | 2 month after final data file | End of July, 2015-18  |
| NIH-specified Statistical Tables and Figures | 10 weeks after final data file | October, 2015-18 |
| Academic Institutional Profiles Tables | 2 months after final data file | September, 2015-18 |
| Additional Reports and Tables | As requested by COR | As requested by COR |
| Ad hoc or Special Data Tables and Analyses | As requested by COR | As requested by COR |