### Appendix V. Project Schedule

|  |  |  |
| --- | --- | --- |
| Task: Study and Survey Design | Start Date | Completion Date |
| Evaluation design | 1/16/2014 | 3/7/2014 |
| Survey instrument draft | 3/7/2014 | 3/28/2014 |
| Review of instrument by WBC representatives | 4/8/2014 | 4/9/2014 |
| Pretest and burden testing | 4/10/2014 | 4/24/2014 |
| Final survey instrument | 4/24/2014 | 4/28/2014 |
| 60-day notice in Federal Register | 6/4/2014 | 8/4/2014 |
| Completion of ICR Part B | 3/7/2014 | 11/25/2014 |
| Completion of ICR Part A and Form 83 - I | 11/25/2014 | 2/17/2015 |
| Submission of ICR for SBA review and revisions | 2/18/2015 | 3/17/2015 |
| Submission of ICR for OMB review | 3/18/2015 | 5/18/2015 |
| Revisions based on OMB review | 5/18/2015 | 5/28/2015 |
| Task: Data Collection | | |
| Select and notify sample sites | 3/18/2015 | 5/18/2015 |
| Prepare client frame and notify clients of study | 5/18/2015 | 6/15/2015 |
| Field survey (e-mail generated from survey system) | 6/18/2015 | 7/18/2015 |
| Survey reminder e-mail generated from system | 6/25/2015 | 6/25/2015 |
| Survey reminder e-mail sent from site leads | 7/9/2015 | 7/12/2015 |
| Task: Analysis and Report | | |
| Outline report | 6/16/2014 | 7/18/2015 |
| Clean data and derive estimates | 7/19/2015 | 8/19/2015 |
| Draft report | 8/19/2015 | 8/31/2015 |
| Final report | 8/31/2015 | 9/18/2015 |