Appendix A-1 Project Schedule

| Intake Data Collection Cohort 1 and Comparison |  |
| --- | --- |
| Program Start | Week 1 |
| Survey Invitation E-mail from SBA/Administrators | Week 1 |
| Survey Start | Week 2 |
| Survey Reminders | Weeks 3-4 |
| Survey Thank you’s | Weeks 3-4 |
| Survey Complete | Week 4 |
| Intake Data Collection Cohort 2 |  |
| Program Start | Week 13* |
| Survey Invitation E-mail from SBA/Administrators | Week 13 |
| Survey Start | Week 14 |
| Survey Reminders | Weeks 15-16 |
| Survey Thank you’s | Weeks 15-16 |
| Survey Complete | Week 16 |
| First Follow-up Collection |  |
| Program End | Week 25* |
| Survey Invitation E-mail from SBA/Administrators | Week 55 |
| Survey Start | Week 56 |
| Survey Reminders | Weeks 57-60 |
| Survey Thank you’s | Weeks 57-60 |
| Survey Complete | Week 60 |
| Participant Interviews |  |
| Interview Invitation E-mail from Administrators | Week 48 |
| Interview Start | Week 49 |
| Interview Complete | Week 50 |
| Second Follow-up Collection |  |
| Survey Invitation E-mail from SBA/Administrators | Week 110 |
| Survey Start | Week 110 |
| Survey Reminders | Weeks 111-114 |
| Survey Thank you’s | Weeks 111-114 |
| Survey Complete | Week 114 |
| Reporting |  |
| First interim report | Week 20 |
| Second interim report | Week 65 |
| Performance report | Week 75 |
| Final report | Week 122 |

*Varies by site and cohort