Appendix I

National Intimate Partner and Sexual Violence

2015-2016 Expert Panel and OMB Timeline (revised)

July 2015 Develop Candidate Panel Member recruitment tiers

August 2015 Review and Vet Panel Candidates

October – December 2015 Finalize Logistics Contract Preparations and Initiate Panel

 Recruitment / Disseminate Background Materials

January 2016 Full Group Meeting #1

February 2016 Subcommittee Meetings #1

March 2016 Full Group Meeting #2

April 2016 Subcommittee Meetings #2

May 2016 Full Group Meeting #3

June 2016 Subcommittee Meetings #3

July/August 2016 In-person Meeting @ CDC

October 2016 Review of Recommendations / Final Full Group Meeting

November 2016 Finalized Plan to Implement

Recommendations

December 2016 Implementation of Plan and OMB PRA

Submitted