**NATIONAL DROUGHT RESPONSE PLAN TASK TRACKER – 7/12/2016**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | | **Lead Coordinating Agency(ies)** | **Action Leader(s)** | **Email Address** |
| **Goal 3: Drought Planning and Capacity Building** | ***Goal Leader: NOAA- Claudia Nierenberg*** | | | [claudia.nierenberg@noaa.gov](mailto:claudia.nierenberg@noaa.gov) |
| **4. Support State, Tribal, Local and Territorial Health Departments** | | HHS-CDC | HHS-CDC- Amy Wolkin | [AJF9@cdc.gov](mailto:AJF9@cdc.gov) |
| ***Develop a guide about the state of drought-related public health activities, including resources to help states prepare for and respond to drought (By March 1, 2018)*** | | | | |
| Literature review to determine most recent scientific knowledge and activities (By December 31, 2016) | | | | |
| Report describing semi-structured in-depth interviews (June 1, 2017) | | | | |
| Report describing assessment of state drought plans (June 30, 2017) | | | | |
| Outline of guide (September 1, 2017) | | | | |
|  | |  |  |  |
| ***Conduct 2 CASPERs in drought-affected states, complete report summarizing drought-related CASPERs (August 1, 2017)*** | | | | |
| Select states for CASPER (July 31, 2016) | | | | |
| Conduct 1st CASPER (October 31, 2016) | | | | |
| Conduct 2nd CASPER (June 30, 2017) | | | | |
| Write Report (August 1, 2017) | | | | |