| ActivitIes |  | Lead |
| --- | --- | --- |
| At approximately 90 days prior to the annual review |
| Contact center with potential review dates. Inform RM/FPO of confirmed dates. |  | NIST MEP Administrative Staff |
| 60 days prior to review |
| 1. Contact the center to inform them of the summary report requirements as established by both the RM/FPO |  | Center Account Manager (RM) and Federal Program Officer (FPO) |
| 2. Begin to assist center in understanding the review process and the performance level as it pertains to CORE |  | Center RM and FPO |
| 30 days prior to review |
| 1. Sends data to the center to incorporate into their summary report. |  | Center FPO |
| 2. Continue to work with the center on preparation of summary report to ensure the center meets submission deadline. |  | Center RM and FPO |
| Two weeks prior to Review Date |
| Center submits the following documents based on performance level (CORE)* Level 1- written response to panel recommendations Level 2/3- center updates, center profile and results section, current year budget including YTD vs. Budget, written response to the last panel report( recommendations) * see appendix at the end of this document for CORE level descriptions. |  | Center |
| 2. Confirms receipt of documentation and follow up with center if there are any questions prior to review day |  | Center RM and FPO |
| Day of Review |
| 1. Conduct annual review with the center either virtually or face to face. |  | Center RM and FPO |
| 2. Outline the annual review report process following the actual review. |  | Center RM and FPO |
| Ten Days Post Review |
| 1. Prepare draft annual review report for internal review and approval |  | Center RM and FPO |
| 30 days Post Review |
| 1. Distributes final annual review report to center, Account manager/Federal Program Officer, Grants Specialist and master Files |  | NIST MEP Administrative Staff |

CORE Level Descriptions

Level 1: Centers have CORE Scores of 61 or greater for two most recent Quarters and are over the $10M curve on the MEP Metric for the 2 most recent quarters. The center only Submit responses to agreed upon Panel Recommendations and may opt to have a face-to-face or virtual annual review, if desire.

Level 2:  Centers that don’t meet the level 1 criteria and have a CORE score of above 41 for the two most recent quarters. The center has the option of a face-to-face or virtual annual review but most submit the response to the Panel recommendations, Financials, Operating Plan Draft and Profile.

Level 3: Center has 40 or below CORE scores for most recent two quarters.  RM notifies centers of performance level and Annual Review recommendations. The center must have a face-to-face annual review and must submit the response to the Panel Recommendations, Financials, Operating Plan, and Profile.