### Appendix C2. 2019 Project Schedule

| Task: Study and Survey Design | Date |
| --- | --- |
| Final Workplan | 11/1/2018 |
| Final Quality Control Plan | 11/1/2018 |
| Final Evaluation Methodology | 12/14/2018 |
| 60-day notice in Federal Register | 10/29/2018 |
| Draft OMB Materials | 11/16/2018 |
| Final OMB Materials | 2/8/2019 |
| SBA sends OMB materials for approval | 4/16/2019 |
| 30-day notice in Federal Register | 4/16/2019 |
| OMB notifies SBA of approval | 9/27/2019 |
| Task: Build Sample Frame |  |
| Letter and template to WBCs | 10/1/2019 |
| Reminder email to WBCs | 10/8/2019 |
| SBA sends 2M completed templates for sample frame | 10/29/2019 |
| Select sample | 11/4/2019 |
| Task: Data Collection |  |
| Introductory letter to sampled clients | 11/6/2019 |
| Email invitation with web link | 11/11/2019 |
| 1st email prompt | 11/18/2019 |
| 2nd email prompt | 11/25/2019 |
| 3rd email prompt | 12/2/2019 |
| Start telephone prompts | 12/9/2019 |
| 4th email prompt | 12/16/2019 |
| Last email prompt | 12/23/2019 |
| Data collection ends | 12/31/2019 |
| Task: Data Delivery and Report |  |
| Clean data and derive estimates | 2/7/2020 |
| Draft report | 2/28/2020 |
| Final report | 3/23/2020 |