|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | | | | | | | | | | | | | | | | | | | | | | | | | | |
|  |  | **2016** | | | | **2017** | | | | **2018** | | | | **2019** | | | | **2020** | | | | **2021** | | | | |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q 4 | Q 1 | Q 2 | Q 3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| **Cohort 1 (Base Period)** | Collect baseline data for Structural Assessments in all three care settings at all three IDSs (TBD, sometime in Fall 2017) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect baseline data for HSOPS, MOSOPS, NHSOPS at all three IDSs (TBD, sometime in Fall 2017) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly baseline clinical outcome facility (TBD, sometime in Fall 2017) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct baseline week long qualitative interview baseline site visits at each IDS (TBD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly real-time team antibiotic review forms in acute care only (TBD-3/31/18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly intervention clinical outcome facility data (TBD- 4/9/18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention data for Structural Assessments in all three care settings at all three IDSs (4/2/18-4/13/18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention data for HSOPS/MOSOPS/NHSOPS at all three IDSs (3/6/18-5/4/18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention week long qualitative interview site visits at each IDS(4/2/18-5/18/18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze pre/post mixed methods evaluation data (5/28/18-6/15/18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft base period report to AHRQ (7/13/18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final base period report to AHRQ (8/16/18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **Cohort 2 (Acute Care)** | Data Collection and Analysis Plan due to AHRQ for OY 1 (TBD ~8/1/2017-10/2/2017) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect baseline data for Acute Care Structural Assessments (12/1/2017-2/1/2018) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect baseline data for HSOPS (12/1/2017-2/1/2018) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly baseline acute care clinical outcome facility data (1/1/2018-3/1/2018) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly real-time team antibiotic review forms during intervention period (3/1/2018-11/30/2018) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly intervention acute care clinical outcome facility data (4/1/2018-12/1/2018) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention data for Acute Care Structural Assessments (12/1/2018-12/21/2018) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention data for HSOPS (12/1/2018-12/21/2018) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze pre/post mixed methods evaluation data (1/2/2019-1/19/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft base period report to AHRQ (TBD February 2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final base period report to AHRQ (TBD March 2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | **2016** | | | | **2017** | | | | **2018** | | | | **2019** | | | | **2020** | | | | **2021** | | | |
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q 2 | Q 3 | Q 4 | Q 1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| **Cohort 3 (Long-Term Care)** | Data Collection and Analysis Plan due to AHRQ for OY 2 (TBD ~8/1/2018-10/2/2018) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect baseline data for LTC Structural Assessments (12/1/2018-2/1/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect baseline data for NHSOPS (12/1/2018-2/1/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly baseline LTC clinical outcome facility data (1/1/2019-3/1/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly real-time team antibiotic review forms during intervention period (3/1/2019-11/30/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly intervention acute care clinical outcome facility data (/1/2019-4/1/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention data for LTC Structural Assessments (12/1/2019-12/21/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention data for NHSOPS (12/1/2019-12/21/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze pre/post mixed methods evaluation data (1/2/2020-1/19/2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft base period report to AHRQ (TBD February 2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final base period report to AHRQ (TBD March 2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **Cohort 4 (Ambulatory Care)** | Data Collection and Analysis Plan due to AHRQ for OY 3 (TBD ~8/1/2019-10/2/2019) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect baseline data for Amb Care Structural Assessments (12/1/2019-2/1/2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect baseline data for MOSOPS (12/1/2019-2/1/2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly baseline Amb care clinical outcome facility data (1/1/2020-3/1/2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect monthly intervention Amb care clinical outcome facility data (4/1/2020-12/1/2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention data for Amb Care Structural Assessments (12/1/2020-12/21/2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect post-intervention data for MOSOPS (12/1/2020-12/21/2020) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze pre/post mixed methods evaluation data (1/2/2021-1/19/2021) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft base period report to AHRQ (TBD February 2021) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final base period report to AHRQ (TBD March 2021) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |