**ATTACHMENT 8**

**GSS Schedule**

|  |  |
| --- | --- |
| **Deliverable/Milestone** | **Due Date** |
| **Conduct GSS (for 2020, 2021, and 2022 survey cycles)** | |
| Revised Survey Operations Plan | 3 months prior to survey launch date |
| Survey Instrument Update | October 8th |
| Survey Launch | Mid-October |
| GSS Screener Page Due Date | End of November |
| GSS Due Date (for all respondents) | End of February |
| Survey Close-out | End of April |
| Data Editing | End of June |
| Data Imputation | End of July |
| Data Files |  |
| Final Edited, Imputed Data File | End of August |
| WebCASPAR Input | End of September |
| Public Use Data Files | End of September |
| NCSES Data Repository Files | Within 1 month of data release |
| Methodology report | Within 3 months after final data file |
| **Conduct FFRDC Postdoc Survey (2018 survey cycle only)** | |
| Survey Instrument Update | End of September |
| Survey Launch | End of October |
| Survey Close-out | End of December |
| FFRDC postdoc data files and draft report | Within 4 weeks after end of data collection |
| NCSES Data Repository Files | Within 1 month of data release |
| **Publications and Data Dissemination (for each survey cycle)** | |
| Draft Data Release Info Brief Concept | 2 weeks after final data file |
| Draft Data Release Info Brief | 2 weeks after NSF concept approval |
| Detailed Statistical Tables (DSTs) Shells, Populated DSTs and Technical Appendices | 2 months after final data file |
| Supplemental DSTs (e-Tables) | 1 month after DSTs release |
| Survey Overview Update | 2 month after final data file |
| NIH-specified Statistical Tables and Figures | 10 weeks after final data file |
| Academic Institutional Profiles Tables | 2 months after final data file |
| Additional Reports and Tables | As requested by COR |
| Ad hoc or Special Data Tables and Analyses | As requested by COR |