**Appendix A-1: Microloan Program Deliverables Schedule**

| **Tasks** | **Deliverables** | **Due/Delivered Date** |
| --- | --- | --- |
| Task 2  | Evaluation Design and Planning |   |
|  | Evaluation Methodology FINAL | 7/17/2020 |
| Task 3  | Data Collection and Analysis |  |
|  | Instrument Design |  |
| Pilot Instruments Completed | 8/31/2020 |
| Instrument FINAL | 9/14/2020 |
| OMB ICR Package and submission | 12/28/2020 |
| Obtain OMB Clearance | 4/12/2021 |
|  | Microloan administrative data analysis and sampling | 3/22/2021 |
| Web surveys and qualitative interviews initiated | 4/13/2021 |
| Web surveys and qualitative interviews completed | 7/12/2021 |
| Data linking and Management | 7/27/2021 |
| Initial descriptive statistics | 8/11/2021 |
| Task 4  | Reports |   |
|  | Report FINAL | 10/8/2021 |
| **COMPLETION DATE** | **11/1/2021** |