Appendix A-1: Microloan Program Deliverables Schedule

| Tasks | Deliverables | Due/Delivered Date |
| --- | --- | --- |
| Task 2 | Evaluation Design and Planning |  |
|  | Evaluation Methodology FINAL | 7/17/2020 |
| Task 3 | Data Collection and Analysis |  |
|  | Instrument Design |  |
|  | Pilot Instruments Completed | 8/31/2020 |
|  | Instrument FINAL | 9/14/2020 |
|  | OMB ICR Package and submission | 12/28/2020 |
|  | Obtain OMB Clearance | 4/12/2021 |
|  | Microloan administrative data analysis and sampling | 3/22/2021 |
|  | Web surveys and qualitative interviews initiated | 4/13/2021 |
|  | Web surveys and qualitative interviews completed | 7/12/2021 |
|  | Data linking and Management | 7/27/2021 |
|  | Initial descriptive statistics | 8/11/2021 |
| Task 4 | Reports |  |
|  | Report FINAL | 10/8/2021 |
| COMPLETION DATE |  | 11/1/2021 |