|  | Start Date | End Date |
| --- | --- | --- |
| ICU and Non-ICU Cohorts |  |  |
| ICU data collection | 4/1/2022 | 10/1/2023 |
| Non-ICU data collection | 4/1/2022 | 10/1/2023 |
| Final Interim Report |  | 12/30/2022 |
| Final Report |  | 6/5/2024 |
| Surgical Services Cohort |  |  |
| Data collection | 1/2/2023 | 7/2/2024 |
| Final Interim Report |  | 9/30/2023 |
| Final Report |  | 7/31/2025 |
| Long-Term Care Facility Cohort |  |  |
| Data collection | 6/1/2023 | 12/30/2024 |
| Final Interim Report |  | 2/28/2024 |
| Final Report |  | 7/31/2025 |