ATTACHMENT 8

GSS Schedule

| ### Deliverable/Milestone | ### Due Date |
| --- | --- |
| ### Conduct GSS (for 2023, 2024, and 2025 survey cycles) |  |
| Revised Survey Operations Plan | 3 months prior to survey launch date |
| GSS Coordinator Confirmation Launch | Mid-September |
| Survey Instrument Update | October 8th |
| Survey Launch | Mid-October |
| GSS Screener Page Due Date | End of November |
| GSS Due Date (for all respondents) | End of February |
| GSS Extension Due Date | Mid-March |
| Survey Close-out | End of April |
| Data Editing | End of June |
| Data Imputation | End of July |
| Data Files |  |
| Final Edited, Imputed Data File | End of August |
| Internet Data Tool Input | End of September |
| Public Use Data Files | End of September |
| NCSES Data Repository Files | Within 1 month of data release |
| Methodology report | Within 3 months after final data file delivery |
| ### Conduct FFRDC Postdoc Survey (2023 and 2025 survey cycles) |  |
| Survey Instrument Update | End of September |
| Survey Launch | Mid-February |
| Survey Deadline | End of March |
| Nonresponse follow-up | Mid-April |
| Survey Close-out | End of August |
| FFRDC postdoc data files and draft report | Within 4 weeks after end of data collection |
| NCSES Data Repository Files | Within 1 month of data release |
| ### Publications and Data Dissemination (for each survey cycle) |  |
| Draft Data Release Info Brief Concept | 2 weeks after final data file |
| Draft Data Release Info Brief | 2 weeks after NSF concept approval |
| Data and Technical Tables | 2 months after final data file |
| Survey Overview Update | 2 months after final data file |
| NIH-specified Statistical Tables and Figures | 10 weeks after final data file |
| Academic Institutional Profiles Tables | 2 months after final data file |
| Additional Reports and Tables | As requested by COR |
| Ad hoc or Special Data Tables and Analyses | As requested by COR |