|  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q 1 | Q 2 | Q 3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Improving Antibiotic Use Cohort | Collect baseline data for Structural Assessments (6/1/2024-8/31/2024) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect baseline data for AHRQ Patient Safety Culture Surveys: MOSOPS (6/1/2024-8/31/2024) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect monthly (March, April, May, June, July, August) baseline EHR data (9/1/2024-9/14/2024) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect monthly (September, October, November) EHR data (12/1/2024-12/14/2024) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect monthly (December, January, February) EHR data (3/1/2025-3/14/2025) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect monthly (March, April, May) EHR data (6/1/2025-6/14/2025) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect monthly (June, July, August) EHR Data (9/1/2025-9/14/2025) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct semi-structured interviews (9/1/2025-11/30/25) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect post-intervention data for Participant Experience Surveys (9/1/2025-11/30/2025) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect post-intervention data for Structural Assessments (9/1/2025-11/30/25) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect post-intervention data AHRQ Patient Safety Culture Surveys: MOSOPS (9/1/2025-11/30/25) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Collect monthly (September, October, November) EHR data (12/1/2025-12/14/2025) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Analyze pre/post mixed methods assessment data (1/1/26-2/15/26) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Draft base period report to AHRQ (5/4/26) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Final base period report to AHRQ (5/25/26) |  |  |  |  |  |  |  |  |  |  |  |  |