## Risk Register
Risk ID | Risk Category | Risk Description ("if then" | Risk Owner | Risk Response Actions | Trigger | Watch Date | Risk Ranking
E-1 | Ecosystem | If de minimus isn't addressed, then we could see further industry collapse | C-Suite and Leadership Team | Create a policy and advocacy committee to support legislative awareness and action | US DOL BLS data indicates continued job losses in relevant NAICS sectors | Quarterly | High
E-2 | Ecosystem | If key partners experience major operational disruption (e.g. loss of funding, loss of key personnel), it could weaken the leadership and productivity of the Engine | C-Suite and Leadership Team | Regular biweekly communication with Leadership team members to ensure awareness of organizational shifts, potential and upcoming, within core partners to understand potential impact to the Engine and ensure timely planning and mitigation | Indications in budget negotiations that forecast funding cuts to State budgets, community college budgets and UNC system budgets programming; changes to legislative body | Biweekly | Low
E-3 | Ecosystem | If funding for the Engines program doesn't continue, some projects will not be brought to fruition | C-Suite and Leadership Team | Proactively reach out to relevant legislators to communicate the importance and impact of Engine's funding to our region of service | Indications in budget negotiations that forecast funding cuts to NSF or Engines programming; changes to legislative body | Quarterly | Medium
E-4 | Ecosystem | If regulatory and environmental policy is poorly informed or not enacted, it will hinder the ability of the Engine to launch products into commercialization and could negatively impact the industry overall | C-Suite and Leadership Team | Create a policy and advocacy committee to support legislative awareness and action and create consumer awareness | Sponsorship of EPR or other legislations that are restrictive to the process of developing sustainable fibers | Quarterly | High
R-1 | Research and Development | If inflation continues, equipment and material prices could deplete Engine resources | Deputy Director (Melissa) and R&D Thrust Leads | Ensure timely purchases to reduce price changes and impacts to overall budgets, create oversight to ensure best procurement practices are being followed, and hold monthly budget review meetings to understand cash flow and available resources | Pricing exceeds budgeted amount by more than 5% | Per purchase exceeding $5,000 | Low
R-2 | Research and Development | If research and development does not move quickly enough, US sustainable products will not be competitive in the market and other countries will consume the majority of market share | Deputy Director (Melissa) and R&D Thrust Leads | Release research funding quickly to allow projects time to mature and hold monthly research team meetings to provide oversight and accountability for research activities and objectives | TRL levels do not advance per project deadlines, Brands discontinue interest in projects to pursue other technologies | Quarterly | Medium
T-1 | Translation | If sustainable fibers cannot be produced within current costing structures, brands will not adopt them | CEO and Translation Thrust Lead (Jeff) | Ensure brand involvement early in pilot projects and formalize commercialization and purchase agreements | Brands are not convinced to participate in early pilots or commit to purchase orders | Per pilot project | High
T-2 | Translation | If capital isn't available to support new business ventures and manufacturing technologies, Engines innovations will not make it to the marketplace | CEO and Translation Thrust Lead (Jeff) | Formalize the economic infrastructure development with partners like NC IDEA, invest in pitch development and marketing to clearly communicate value proposition and attract a diverse funding base | Decrease in capital investments across Engines activities | Quarterly | Medium
T-3 | Translation | If navigating the complexity of intellectual property ownership becomes untenable, then we can't maximize shared knowledge and incentivize businesses to be members | CEO and Translation Thrust Lead (Jeff) | What has worked before for similar organizations, having good policies around IP management, strong board oversight and building strong relationships to build trust | Non participation in the Engine by emerging R&D Leaders | Quarterly | Low
W-1 | Workforce | If industry continues to shrink, fewer jobs will be available | Deputy Director (Molly) and Workforce Thrust Lead (Jasmine) | Involve brands and manufacturers early in the process and pilots to create stable supply and demand pipelines for Engines innovations. Policy and advocacy to continue to support regulation (trade policy, Barry amendment, etc) that supports domestic production | US DOL BLS data indicates continued job losses in relevant NAICS sectors | Quarterly | Medium
W-2 | Workforce | If products aren't commercialized, the manufacturing sector will not grow and new jobs won't be created | Deputy Director (Molly) and Workforce Thrust Lead (Jasmine) | Involve brands and manufacturers early in the process and pilots to create stable supply and demand pipelines for Engines innovations. Policy and advocacy to continue to support regulation (trade policy, Barry amendment, etc) that supports domestic production | Early pilots are not successful; brands are not convinced to participate in early pilots | Quarterly | High
W-3 | Workforce | If K-12 education systems don't see the importance and/or future of textiles, they won't support early childhood and vocational education that will build a workforce pipeline for these industries | Deputy Director (Molly) and Workforce Thrust Lead (Jasmine) | Use data to show decision makers and education leaders the value of this industry and future career pathways | NC DPI discontinues curriculum discussions and development | May-June 2024 | Medium

## Defintions
List and Define the Meta Data Fields used in the risk register. This includes the options where responses may vary
NAICS Codes